{"text_format":"1","workbook":"xlsx","n_sheets":25,"sheets":["APGI","DUKE","EEI","ENTERGY","E.ON-LGEE","FPL","GTC","IESO","ITC","ISO-NE","JEA","MAPPCOR","MEAG","MISO","NBSO","NY-ISO","PJM","POWERSOUTH","PEC","PEF","SCEG","SCPSA","SOCO","SPP","TVA"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":91,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"APGI","index":0,"n_rows":6,"n_cols":19,"rows_kept":6,"cut":false,"hidden":false,"merged":[[3,16,4,16],[3,4,3,5],[3,6,4,6],[3,8,4,8],[3,18,4,18],[3,7,4,7],[3,9,3,10],[3,11,3,14],[3,17,4,17],[3,15,4,15],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["APGI","NC","n/a",null,"n/a",null,null,null,null,null,null,null,null,null,null,null,null,null,"No new facilities"]

{"sheet":"DUKE","index":1,"n_rows":9,"n_cols":19,"rows_kept":9,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["Duke Energy Carolinas","NC",306151,"6PISGAH     230.0",306159,"6SHILOH     230.0",1,230,22,null,null,null,null,null,null,2013,"Under Construction","Reliability","Conductor upgrade"]
["Duke Energy Carolinas","NC",306151,"6PISGAH     230.0",306159,"6SHILOH     230.0",2,230,22,null,null,null,null,null,null,2013,"Under Construction","Reliability","Conductor upgrade"]
["Duke Energy Carolinas","NC",306152,"6PL GRDN    230.0",304332,"6ASHEB     230.0",1,230,20,null,null,null,null,null,null,2011,"Under Construction","Reliability","New tie line to CPLE"]
["Duke Energy Carolinas","NC",306461,"CLFSDTAP    500.0",null,null,null,500,null,null,null,null,null,null,null,2011,"Under Construction","Reliability","New station for Cliffside 6 generator"]

{"sheet":"EEI","index":2,"n_rows":6,"n_cols":19,"rows_kept":6,"cut":false,"hidden":false,"merged":[[5,1,5,18],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,17,4,17],[3,18,4,18],[3,9,3,10],[3,11,3,14],[3,15,4,15],[3,16,4,16]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["EEI","**NONE**"]

{"sheet":"ENTERGY","index":3,"n_rows":82,"n_cols":19,"rows_kept":82,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new facilities (161 kV and above) that are projected to be in-service by 2020.  It should be noted whether these are committed or planned."]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["Entergy","TX",334442,"Gulfway 230kV",334434,"Sabine 230kV ",1,230,5.5,null,null,null,null,null,null,2010,"Complete","Reliability","Construct new 230 kV line"]
["Entergy","LA",335536,"Addis 230kV",303000,"Cajun 230kV",1,230,0.1,null,null,null,null,null,null,2010,"Construction","Reliability","Upgrade 230 kV line"]
["Entergy","AR",337905,"East Russelville 161kV",337904,"South Russelville 161kV",1,161,4.0999999999999996,null,null,null,null,null,null,2010,"Complete","Reliability","Upgrade 161 kV line"]
["Entergy","AR",337912,"Arkansas Nuclear One 161kV",337906,"North Russelville 161kV",1,161,8.7899999999999991,null,null,null,null,null,null,2010,"Complete","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338033,"Parkin 161kV",338041,"Twist 161kV",1,161,8.0500000000000007,null,null,null,null,null,null,2010,"Planned","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338131,"Melbourne 161kV",338132,"Sage 161kV",1,161,4.7699999999999996,null,null,null,null,null,null,2010,"Construction","Reliability","Upgrade 161 kV line"]
["Entergy","TX",334069,"Lewis Creek 230kV",334072,"Lewis Creek 138kV",1,"230/138kV ","n/a",null,null,null,null,null,null,2011,"Construction","Reliability","Convert line to 230 kV operation and add auto at Lewis Creek"]
["Entergy","TX",334069,"Lewis Creek 230kV",334085,"Peach Creek 230kV",1,230,12.39,null,null,null,null,null,null,2011,"Construction","Reliability","Convert line to 230 kV operation and add auto at Lewis Creek"]
["Entergy","TX",334085,"Peach Creek 230kV",334206,"Jacinto 230kV",1,230,16.489999999999998,null,null,null,null,null,null,2011,"Construction","Reliability","Convert line to 230 kV operation and add auto at Lewis Creek"]
["Entergy","TX",334362,"Inland Orange 230kV",334361,"McLewis 230kV",1,230,6.55,null,null,null,null,null,null,2011,"Planned","Reliability","Upgrade 230 kV line"]
["Entergy","TX",334363,"Hartburg 230kV",334362,"Inland Orange 230kV",1,230,3.98,null,null,null,null,null,null,2011,"Planned","Reliability","Upgrade 230 kV line"]
["Entergy","LA",335381,"Meaux 230 kV",335380,"Meaux 138 kV",1,"230/138kV ","n/a",null,null,null,null,null,null,2011,"Construction","Reliability","Acadiana Load Pocket Project Construct new 230 kV line and add auto at Meaux"]
["Entergy","LA",336010,"Bayou Laboutte 500 kV",336011,"Bayou Laboutte 230 kV",1,"500/230kV ","n/a",null,null,null,null,null,null,2011,"Planned","Reliability","Construct new 500-230 kV substation and 230 kV line "]
["Entergy","LA",336011,"Bayou Laboutte 230kV",336000,"Iberville 230kV",1,230,1.5,null,null,null,null,null,null,2011,"Planned","Reliability","Construct new 500-230 kV substation and 230 kV line "]
["Entergy","MS",337000,"McAdams 230kV",337015,"Pickens 230kV",1,230,16.3,null,null,null,null,null,null,2011,"Construction","Reliability","Add 2nd 500-230 kV auto and construct new 230 kV line"]
["Entergy","MS",337009,"McAdams 500 kV",337000,"McAdams 230 kV",2,"500/230kV ","n/a",null,null,null,null,null,null,2011,"Construction","Reliability","Add 2nd 500-230 kV auto and construct new 230 kV line"]
["Entergy ","LA",337376,"Sarepta 345 kV",337363,"Sarepta 115 kV",1,"345/115kV ","n/a",null,null,null,null,null,null,2011,"Construction","Reliability","Construct new 345-115 kV substation"]
["Entergy ","AR",338140,"Holland Bottoms 500 kV",338016,"Holland Bottoms 115 kV",1,"500/115kV ","n/a",null,null,null,null,null,null,2011,"Planned","Reliability","Construct new 500-161-115 kV substation"]
["Entergy","AR",338682,"Osage Creek 161kV",338099,"Grandview 161kV",1,161,5,null,null,null,null,null,null,2011,"Planned","Reliability","Construct new 161 kV line"]
["Entergy","LA",500776,"Sellers Rd 230kV",335381,"Meaux 230kV",1,230,9.3000000000000007,null,null,null,null,null,null,2011,"Construction","Reliability","Construct new 230 kV line"]
["Entergy","LA",335190,"Nelson 230kV",303101,"Moss Bluff 230kV",1,230,7,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line"]
["Entergy","LA",335771,"Loblolly 230kV",336140,"Hammond 230kV",1,230,26.3,null,null,null,null,null,null,2012,"Construction","Reliability","Construct new 230 kV line"]
["Entergy","LA",336069,"Bayou Steel 230kV",336192,"Tezcuco 230kV",1,230,10,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line"]
["Entergy","LA",336086,"Alliance 230 kV",336085,"Alliance 115kV",1,"230/115kV","n/a",null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line and add auto at Alliance"]
["Entergy","LA",336088,"Oakville 230kV",336086,"Alliance 230kV",1,230,10.3,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line and add auto at Alliance"]
["Entergy","LA",336261,"Peters Road 230kV",336088,"Oakville 230kV",1,230,6.6,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line"]
["Entergy","MS",336830,"Baxter Wilson 500 kV",336800,"Baxter Wilson 115 kV",2,"500/115kV ","n/a",null,null,null,null,null,null,2012,"Construction","Reliability"]
["Entergy","MS",337059,"South Grenada 230 kV",337063,"South Grenada 115 kV",1,"230/115kV ","n/a",null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line and add auto at South Grenada"]
["Entergy","MS",337120,"Tillatoba 230kV",337059,"South Grenada 230kV",1,230,19,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 230 kV line and add auto at South Grenada"]
["Entergy","AR",337904,"South Russelville 161kV",505508,"Dardanelle 161kV",1,161,11.09,null,null,null,null,null,null,2012,"Planned","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338015,"Holland Bottoms 161kV",337940,"Hamlet 161kV",1,161,20,null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 161 kV line"]
["Entergy","AR",338140,"Holland Bottoms 500 kV",338015,"Holland Bottoms 161 kV",1,"500/161kV ","n/a",null,null,null,null,null,null,2012,"Planned","Reliability","Construct new 500-161-115 kV substation"]
["Entergy","AR",338163,"Ebony South 161kV","n/a","n/a","n/a",161,"n/a",null,null,null,null,null,null,2012,"Planned","Reliability","Install  5 breaker ring bus at Ebony South and reconfigure substation to include two new lines"]
["Entergy","AR",338186,"Monette 161kV",338204,"Paragould 161kV",1,161,16.73,null,null,null,null,null,null,2012,"Planned","Reliability","Upgrade 161 kV line"]
["Entergy","LA",502421,"Labbe 230kV",500776,"Sellers Rd 230kV",1,230,15.7,null,null,null,null,null,null,2012,"Planned","Reliability","Acadiana Load Pocket Project Construct new 230 kV line"]
["Entergy","LA",335568,"Willow Glen 230kV",335580,"Conway 230kV",1,230,15,null,null,null,null,null,null,2013,"Planned","Reliability","Construct new 230 kV line"]
["Entergy","MS",337149,"Church Road 230kV",337140,"Getwell 230kV",1,230,16,null,null,null,null,null,null,2013,"Planned","Reliability","Construct new 230 kV line"]
["Entergy","LA",337420,"Sterlington 500kV",337414,"Sterlington 115kV",3,"500/115kV ","n/a",null,null,null,null,null,null,2013,"Construction","Reliability","Replace 500-115kV auto"]
["Entergy","TX",334325,"Hartburg 500 kV",334363,"Hartburg 230 kV",2,"500/230kV ","n/a",null,null,null,null,null,null,2014,"Conceptual","Reliability","Construct new 230 kV line and add 2nd auto at Hartburg"]
["Entergy","TX",334363,"Hartburg 230kV",334429,"Chisolm Rd 230kV",1,230,15,null,null,null,null,null,null,2014,"Conceptual","Reliability","Construct new 230 kV line and add 2nd auto at Hartburg"]
["Entergy","LA",303101,"Moss Bluff 230kV",335209,"Lake Charles Bulk 230kV",1,230,15.28,null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct new 230 kV line and 230 kV switching station"]
["Entergy","TX",334204,"China 230kV",334327,"Amelia 230kV",2,230,11,null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct 2nd China to Amelia 230 kV line"]
["Entergy","TX",334326,"Cypress 230kV",334324,"Jacinto 230kV",1,230,53,null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct new 230 kV line"]
["Entergy","MS",337132,"Senatobia Industrial 230kV",337133,"Senatobia Industrial 115kV",1,"230/115kV","n/a",null,null,null,null,null,null,2015,"Planned","Reliability","Construct new 230 kV line and add auto at Senatobia Industrial"]
["Entergy","MS",337140,"Getwell 230kV",337132,"Senatobia Industrial 230kV",1,230,26,null,null,null,null,null,null,2015,"Planned","Reliability","Construct new 230 kV line and add auto at Senatobia Industrial"]
["Entergy","LA",337377,"Sterlington 230kV",337382,"Drew 230kV",1,230,16.7,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337381,"Rilla 230kV",337386,"Rilla 115kV",1,"230/115kV ","n/a",null,null,null,null,null,null,2015,"Conceptual","Reliability","Add 230-115 kV auto"]
["Entergy","LA",337381,"Rilla 230kV",337387,"Selman Field 230kV",1,230,10.25,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337382,"Drew 230kV",337383,"Cheniere 230kV",1,230,2.98,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337383,"Cheniere 230kV",337384,"Riser 230kV",1,230,6.62,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337384,"Riser 230kV",337412,"Frost Craft 230kV",1,230,1.93,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337387,"Selman Field 230kV",337377,"Sterlington 230kV",1,230,15.4,null,null,null,null,null,null,2015,"Conceptual","Reliability","Monroe Area: Convert to 230kV"]
["Entergy","LA",337412,"Frost Craft 230kV",337385,"Frost Craft 115kV",1,"230/115kV ","n/a",null,null,null,null,null,null,2015,"Conceptual","Reliability","Add 230-115 kV auto"]
["Entergy","LA",337420,"Sterlington 500kV",337377,"Sterlington 230kV",1,"500/230kV ","n/a",null,null,null,null,null,null,2015,"Conceptual","Reliability","Add 500-230 kV auto"]
["Entergy","AR",338130,"Calico Rock 161kV",338131,"Melbourne 161kV",1,161,16.63,null,null,null,null,null,null,2015,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338156,"Viney Slough 500 kV",338157,"Viney Slough 161 kV",1,"500/161 kV ","n/a",null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct new 500-161 kV substation"]
["Entergy","AR",338157,"Viney Slough 161 kV",338170,"Jonesboro 161kV",1,161,11.59,null,null,null,null,null,null,2015,"Conceptual","Reliability","Upgrade 161kV line"]
["Entergy","AR",338157,"Viney Slough 161 kV",338707,"Trumann West 161kV",1,161,5.03,null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct new 161 kV line"]
["Entergy","AR",338157,"Viney Slough 161 kV",505420,"Hergett 161kV",2,161,3.27,null,null,null,null,null,null,2015,"Conceptual","Reliability","Construct new 161 kV line"]
["Entergy","AR",338170,"Jonesboro 161kV",505418,"Jonesboro SPA 161kV",1,161,0.84,null,null,null,null,null,null,2015,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338707,"Trumann West 161kV",338169,"Trumann 161kV",1,161,6.48,null,null,null,null,null,null,2015,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","AR",505460,"Bullshoals 161kV",338813,"Midway 161kV",1,161,23.88,null,null,null,null,null,null,2015,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","TX",334320,"Cypress 500 kV",334326,"Cypress 230 kV",3,"500/230kV ","n/a",null,null,null,null,null,null,2017,"Conceptual","Reliability","Add 2nd auto"]
["Entergy","TX",334326,"Cypress 230kV",334328,"Bevil 230kV",1,230,12.95,null,null,null,null,null,null,2017,"Conceptual","Reliability","Upgrade 230 kV line"]
["Entergy","TX",334327,"Amelia 230kV ",334360,"Helbig 230kV",1,230,10.3,null,null,null,null,null,null,2017,"Conceptual","Reliability","Upgrade 230 kV line"]
["Entergy","TX",334328,"Bevil 230kV",334327,"Amelia 230kV",1,231,5.68,null,null,null,null,null,null,2017,"Conceptual","Reliability","Upgrade 230 kV line"]
["Entergy","AR",337905,"East Russelville 161kV",337906,"North Russelville 161kV",1,161,3.19,null,null,null,null,null,null,2017,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","MS",337132,"Senatobia Industrial 230kV",337123,"Batesville 230kV",1,230,22,null,null,null,null,null,null,2018,"Conceptual","Reliability","Construct new 230 kV line"]
["Entergy","AR",337993,"Gobell 230kV",337992,"Gobell 115kV",1,"230/115kV","n/a",null,null,null,null,null,null,2018,"Conceptual","Reliability","Construct new 230-115 kV substation"]
["Entergy","AR",338125,"Mt Home 161kV",338814,"Southland 161kV",1,161,1.38,null,null,null,null,null,null,2018,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","AR",338226,"Jim Hill 161kV",338202,"Datto 161kV",1,161,40,null,null,null,null,null,null,2018,"Conceptual","Reliability","Construct new 161 kV line"]
["Entergy","AR",338813,"Midway 161kV",338125,"Mt Home 161kV",1,161,4.41,null,null,null,null,null,null,2018,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","AR",505448,"Norfork 161kV",338130,"Calico Rock 161kV",1,161,8.1199999999999992,null,null,null,null,null,null,2018,"Conceptual","Reliability","Upgrade 161 kV line"]
["Entergy","LA",336190,"Gypsy 230kV",336155,"Hooker 230kV",1,230,4.3499999999999996,null,null,null,null,null,null,2020,"Conceptual","Reliability","Reconfigure area 230 kV"]
["Entergy","LA",336225,"Waggaman 230kV",336154,"Waterford 230kV",1,230,9.4,null,null,null,null,null,null,2020,"Conceptual","Reliability","Convert line to 230 kV operation"]
["Entergy","LA",336225,"Waggaman 230kV",336250,"Ninemile 230kV",1,230,8.5,null,null,null,null,null,null,2020,"Conceptual","Reliability","Convert line to 230 kV operation"]
["Entergy","LA",336435,"A B Patterson 230 kV",336412,"A B Patterson 115 kV",1,"230/115kV","n/a",null,null,null,null,null,null,2020,"Conceptual","Reliability","Add 230-115 kV auto"]

{"sheet":"E.ON-LGEE","index":4,"n_rows":6,"n_cols":19,"rows_kept":6,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["LGEE","KY",324145,"5GRAHMVL",360496,"5C-33",2,161,2,null,null,null,null,null,null,"1905-07-04","Under Construction  ","Reliability","Add second Grahamville-DOE 161kV line"]

{"sheet":"FPL","index":5,"n_rows":35,"n_cols":19,"rows_kept":35,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["FPL","FL",400308,"Fruitville",400352,"Ringling",1,230,4.3099999999999996,"1431","ACSR/AW",759,null,759,null,2011,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",400123,"Emerson",400266,"Midway",1,230,15,null,null,526,null,526,null,2010,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",400466,"Orangedale",400841,"Millcreek",1,230,0.33,null,null,null,null,null,null,2013,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",400571,"Deltona",400469,"Sanford",1,230,14.5,null,null,526,null,526,null,2010,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",401794,"Bobwhite",400352,"Ringling",2,230,0.10000000149011612,"1431","ACSR/AZ",637,null,637,null,2012,"Planned","Reliability","New line"]
["FPL","FL",400351,"OrangeRiv",400919,"Orangetree",2,230,0.10000000149011612,"1431","ACSR/AW",759,null,759,null,2013,"Planned","Reliability","New line"]
["FPL","FL",401794,"Bobwhite",400352,"Ringling",1,230,0.10000000149011612,"1431","ACSR/AZ",637,null,637,null,2012,"Planned","Reliability","New line"]
["FPL","FL",401794,"Bobwhite",400348,"Laurelwood",1,230,0.10000000149011612,"1431","ACSR/AZ",637,null,637,null,2012,"Planned","Reliability","New line"]
["FPL","FL",401794,"Bobwhite",400349,"Manatee",1,230,13,"2-1431","ACSR/AW",1195,null,1195,null,2012,"Planned","Reliability","New line"]
["FPL","FL",401725,"Gaco",401054,"Pirolo",1,230,12.5,"1431","ACSR/AW",759,null,759,null,2010,"Under Construction","Reliability","New line"]
["FPL","FL",400470,"St Johns",401062,"Pellicer",1,230,8,"1431","ACSR/AW",759,null,759,null,2013,"Planned","Reliability","New line"]
["FPL","FL",400712,"O'Neil",410024,"Kingsland",1,230,7.5,"1431","ACSR/AW",759,null,759,null,2012,"Under Construction","Reliability","New line"]
["FPL","FL",400750,"Alico",400344,"Ft Myers",1,230,19.5,"1431","ACSR/AW",759,null,759,null,2011,"Under Construction","Reliability","New line"]
["FPL","FL",400750,"Alico",400344,"Ft Myers",1,230,1,"1431","ACSR/AW",759,null,759,null,2011,"Under Construction","Reliability","New line"]
["FPL","FL",400119,"Turkey Pt",401014,"Prince230",1,230,11,"1431","ACSR/AZ",759,null,759,null,2011,"Under Construction","Reliability","New line"]
["FPL","FL",400468,"Putnam",400462,"Rice",1,230,15.53,null,null,588,null,588,null,2013,"Planned","Reliability","Line upgrade"]
["FPL","FL",400468,"Putnam",400398,"Hudson",1,230,9.8490000000000002,null,null,747,null,747,null,2015,"Planned","Reliability","Line upgrade"]
["FPL","FL",400817,"FPL120G1",406496,"Sampson",1,230,null,null,null,588,null,588,null,2012,"Planned","Reliability","Line upgrade"]
["FPL","FL",400266,"Midway",400272,"St Lucie",1,230,11.6,null,null,1111,null,1111,null,2011,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",400266,"Midway",400272,"St Lucie",2,230,11.7,null,null,1111,null,1111,null,2011,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",400266,"Midway",400272,"St Lucie",3,230,11.8,null,null,1111,null,1111,null,2011,"Under Construction","Reliability","Line upgrade"]
["FPL","FL",410119,"Clear Sky",410120," autotransformer",1,"500/230",0,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",410119,"Clear Sky",410120," autotransformer",2,"500/230",0,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",410120,"Clear Sky",400120,"Levee",1,500,43,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",410120,"Clear Sky",400120,"Levee",2,500,43,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",410119,"Clear Sky",400109,"Levee",1,230,43,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",410119,"Clear Sky",400105,"Davis",1,230,21,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",400356,"Duval",410014,"Series Comp ",null,500,0,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",400356,"Duval",410014,"Series Comp ",null,500,0,null,null,null,null,null,null,2020,"Planned","Reliability","Nuclear Plant"]
["FPL","FL",400535,"Corbett",401225,"Germantown",1,230,38.1,null,null,705,null,705,null,2011,"Under Construction","Reliability","New line"]

{"sheet":"GTC","index":6,"n_rows":2,"n_cols":1,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
[]
["GTC'S data is reflected within Southern Company's data"]

{"sheet":"IESO","index":7,"n_rows":32,"n_cols":19,"rows_kept":32,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["IESO","Ontario",152000,"Hanmer",156014,"Claireville",1,500,215,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,151054,"Lakehead",152061,"Wawa",1,220,247.3,null,null,null,null,null,null,2015,"Planned","R"]
[null,null,151054,"Lakehead",152061,"Wawa",2,220,247.3,null,null,null,null,null,null,2015,"Planned","R"]
[null,null,152049,"Mississagi",152000,"Hanmer",1,500,130.5,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,160059,"Lambton",160062,"Longwood",1,220,47.2,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,160069,"Lambton",160062,"Longwood",1,220,47.2,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,152074,"Wawa",152118,"Third Line",1,220,103.1,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,152074,"Wawa",152118,"Third Line",2,220,103.1,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,156000,"Bowmanville",156001,"Cherrywood",5,500,28.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,156000,"Bowmanville",156001,"Cherrywood",6,500,28.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,155069,"St. Lawrence",154050,"Hawthorne",1,220,46.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,155069,"St. Lawrence",154050,"Hawthorne",2,220,46.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,151391,"Nipigon",151393,"Crow River",1,220,261,null,null,null,null,null,null,2013,"Conceptual","R"]
[null,null,160055,"Chatham",160062,"Longwood",1,220,51.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,160055,"Chatham",160062,"Longwood",2,220,51.6,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,152118,"Third Line",152074,"Mississagi",1,220,47.2,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,152118,"Third Line",152074,"Mississagi",2,220,47.2,null,null,null,null,null,null,2015,"Conceptual","R"]
[null,null,158171,"Ingersoll",158168,"Karn",1,220,9.3000000000000007,null,null,null,null,null,null,2011,"Under Construction ","R"]
[null,null,158172,"Ingersoll",158169,"Karn",1,220,9.3000000000000007,null,null,null,null,null,null,2011,"Under Construction ","R"]
[null,null,160157,"Sandwitch Junction",160060,"Lauzon TS",1,220,7.5,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,160158,"Sandwitch Junction",160061,"Lauzon TS",1,220,7.5,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,158000,"Milton",159000,"Bruce",1,500,115.6,null,null,null,null,null,null,2013,"Planned","R"]
[null,null,158000,"Milton",159001,"Bruce",1,500,115.6,null,null,null,null,null,null,2013,"Planned","R"]
[null,null,157280,"Allanburg",158069,"Middleport",1,220,47.2,null,null,null,null,null,null,"Unknown","Under Construction ","R","The construction is on hold"]
[null,null,157281,"Allanburg",158071,"Middleport",1,220,47.2,null,null,null,null,null,null,"Unknown","Under Construction ","R","The construction is on hold"]
[null,null,null,"Oshawa TS",null,null,null,"500/220",null,null,null,null,null,null,null,2016,"Conceptual","R"]
[null,null,null,"Karn TS",null,null,null,"500/220",null,null,null,null,null,null,null,2011,"Under Construction ","R"]

{"sheet":"ITC","index":8,"n_rows":5,"n_cols":19,"rows_kept":5,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]

{"sheet":"ISO-NE","index":9,"n_rows":45,"n_cols":19,"rows_kept":45,"cut":false,"hidden":false,"merged":[[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,9,3,10],[39,18,40,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[36,18,37,18]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["ISO-NE","ME",100089,"South Gorham 345 kV",100165,"South Gorham 115 kV",2,"345/115","N/A",null,null,null,null,null,null,2010,"Under Construction","Reliability","New second transformer"]
["ISO-NE","ME",100002,"Orrington 345 kV",100092,"Albion Road 345 kV",1,345,59,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100092,"Albion Road 345 kV",100005,"Cooper Mills 345 kV",1,345,21,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100005,"Cooper MIlls 345 kV",100095,"Larrabee Rd 345 kV",1,345,34,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100095,"Larrabee Rd 345 kV",100087,"Surowiec 345 kV",1,345,17,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100092,"Albion Road 345 kV",100247,"Albion Road 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New substation & transformer"]
["ISO-NE","ME",100095,"Larrabee Rd 345 kV",100118,"Gulf Island 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New substation & transformer"]
["ISO-NE","ME",100087,"Surowiec 345 kV",100007,"Raven Farm 345 kV",1,345,12,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100089,"South Gorham 345 kV",100098,"Maguire Road 345 kV",1,345,21,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100098,"Maguire Road 345 kV",103710,"Three Rivers 345 kV",1,345,27,null,null,null,null,null,null,2012,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","ME",100007,"Raven Farm 345 kV",100134,"Raven Farm 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New substation & transformer"]
["ISO-NE","ME",100098,"Maguire Road 345 kV",100163,"Maguire Road 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New substation & transformer"]
["ISO-NE","NH",104095,"Deerfield 345 kV",104506,"Deerfield 115 kV",2,"345/115","N/A",null,null,null,null,null,null,2012,"Under Construction","Reliability","New second transformer"]
["ISO-NE","VT",107040,"Vernon 345 kV",107050,"Vernon 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2011,"Under Construction","Reliability","New substation & transformer"]
["ISO-NE","VT",107040,"Vernon 345 kV",107010,"Coolidge 345 kV",1,345,51,null,null,null,null,null,null,2011,"Under Construction","Reliability","2-954 ACSR (via Newfane)"]
["ISO-NE","MA",111133,"Carver 345 kV",111134,"Long Trm LSM 345 kV",1,345,null,null,null,null,null,null,null,2012,"Planned","Reliability"]
["ISO-NE","MA",111134,"Long Trm LSM 345 kV",111135,"Long Trm LSM 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New transformer"]
["ISO-NE","MA",113266,"Pratts Junction 230 kV",113292,"Pratts Junction 115 kV",2,"230/115","N/A",null,null,null,null,null,null,2011,"Planned","Reliability","New second transformer"]
["ISO-NE","MA",113001,"Bear Swamp 230 kV",113008,"Bear Swamp 115 kV",2,"230/115","N/A",null,null,null,null,null,null,2011,"Planned","Reliability","New second transformer"]
["ISO-NE","MA/VT",113001,"Bear Swamp 230 kV",113266,"Pratts Jct 230 kV",1,230,74,null,null,null,null,null,null,2011,"Planned","Reliability","Retension existing line"]
["ISO-NE","MA",113265,"Wachusett 345 kV",113299,"Wachusett 115 kV",3,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New third transformer"]
["ISO-NE","MA",115447,"Auburn 345 kV",115453,"Auburn 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New second transformer"]
["ISO-NE","MA",116081,"Agawam 345 kV",116152,"Agawam 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2013,"Planned","Reliability","New substation & transformers"]
["ISO-NE","MA",116081,"Agawam 345 kV",116152,"Agawam 115 kV",2,"345/115","N/A",null,null,null,null,null,null,2013,"Planned","Reliability","New substation & transformers"]
["ISO-NE","MA",116045,"Ludlow 345 kV",116081,"Agawam 345 kV",1,345,17,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","MA",116045,"Ludlow 345 kV",116120,"Ludlow 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2013,"Planned","Reliability","Two replacement transformers"]
["ISO-NE","MA",116045,"Ludlow 345 kV",116120,"Ludlow 115 kV",2,"345/115","N/A",null,null,null,null,null,null,2013,"Planned","Reliability","Two replacement transformers"]
["ISO-NE","MA",116081,"Agawam 345 kV",119116,"North Bloomfield 345 kV",1,345,18,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","MA",119116,"North Bloomfield 345 kV",119246,"Frost Bridge 345 kV",1,345,35,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","MA",119246,"Frost Bridge 345 kV",120992,"Frost Bridge 115 kV",2,"345/115","N/A",null,null,null,null,null,null,2013,"Planned","Reliability","New second transformer"]
["ISO-NE","CT",119064,"Card Street 345 kV",119051,"Lake Road 345 kV",1,345,29,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","CT",119194,"Millstone 345 kV",119064,"Card Street 345 kV",1,345,29,null,null,null,null,null,null,2013,"Planned","Reliability","Millstone-Manchester line tapped into Card Street"]
["ISO-NE","CT",119064,"Card Street 345 kV",119077,"Manchester 345 kV",1,345,20,null,null,null,null,null,null,2013,"Planned","Reliability"]
["ISO-NE","CT/RI",119051,"Lake Road 345 kV",117001,"West Farnum 345 kV",1,345,25,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]
["ISO-NE","MA",114734,"Brayton Point 345 kV",114900,"Plainville 345 kV",1,345,20,null,null,null,null,null,null,2011,"Planned","Reliability","Brayton Point-Bellingham line tapped into Plainville"]
["ISO-NE","MA",114900,"Plainville 345 kV",114733,"Bellingham 345 kV",1,345,15,null,null,null,null,null,null,2011,"Planned","Reliability"]
["ISO-NE","MA",114900,"Plainville 345 kV",114865,"Plainville 115 kV",1,"345/115","N/A",null,null,null,null,null,null,2011,"Planned","Reliability","New substation & transformer"]
["ISO-NE","RI",117301,"Kent County 345 kV",117332,"Kent County 115 kV",3,"345/115","N/A",null,null,null,null,null,null,2012,"Planned","Reliability","New third transformer"]
["ISO-NE","RI",117301,"Kent County 345 kV",117001,"West Farnum 345 kV",1,345,17,null,null,null,null,null,null,2012,"Planned","Reliability","2-954 ACSR"]
["ISO-NE","MA/RI",113264,"Millbury 345 kV",117001,"West Farnum 345 kV",1,345,21,null,null,null,null,null,null,2013,"Planned","Reliability","2-1590 ACSR"]

{"sheet":"JEA","index":10,"n_rows":7,"n_cols":19,"rows_kept":7,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["JEA","FLORIDA",404953,"GEC",404855,"Nocatee",30,230,4.4000000000000004,null,null,null,null,null,null,"Dec 1, 2014","Planned","Reliability","GEC = Greenland Energy Center"]
[null,null,404780,"Jax Heights",405015,"Yellow Water",1,230,11,null,null,null,null,null,null,"Dec 1, 2012","Planned","Reliability"]

{"sheet":"MAPPCOR","index":11,"n_rows":2,"n_cols":1,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
[]
["MAPPCOR has deemed this information as CEII"]

{"sheet":"MEAG","index":12,"n_rows":2,"n_cols":1,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
[]
["MEAG'S data is reflected within Southern Company's data"]

{"sheet":"MISO","index":13,"n_rows":122,"n_cols":20,"rows_kept":122,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["MISO","WI",699818,"NMA",699829,"CARDINAL",1,345,20.545999999999999,null,null,null,null,null,null,"2018-12-31","Proposed","Multi Value","P3127-Construct a new North Madison-Cardinal 345kV line"]
["MISO","WI",693636,"NORTH345",693607,"EAST345",2,345,35.5,null,null,null,null,null,null,"2018-06-01","Proposed","Reliability","P3206-1) Construct a new East 345 & 138 kV substation\n2) Install a new 345/138 kV transformer at East\n3) Loop Edgewater-South Fond du Lac, Edgewater-Cedarsauk, Sheboygan Energy Center-Granville \n    345 kV lines into East\n4) Loop the South Sheboygan Falls-Mullet River 138 kV line into East 138 kV\n5) Construct a new 138 kV line from East to Plymouth #4\n6) Construct a new 138 kV line from Plymouth #4 to Howards Grove\n7) Construct a new 138 kV line from Howards Grove to Erdman\n8) Convert the existing Forest Junction-Howards Grove-Plymouth #4 138 kV line and the \n    northern portion of the existing Plymouth #4-Holland 138 kV line to 345 kV\n9) Terminate the not-converted Holland 138 kV line at East 138 kV\n10) Terminate the southern end of the converted 345 kV line at East  \n11) Construct a new North 345 kV substation\n12) Loop the converted 345 kV line into North 345 kV substation\n13) Loop the Point Beach-Forest Juction, Point Beach-Sheboygan Energy Center 345 kV lines into North\n14) Uprate East-Cedarsauk 345 kV line to 960 MVA for SN/SE"]
["MISO","WI",693636,"NORTH345",699304,"FORST",1,345,12.88,null,null,null,null,null,null,"2018-06-01","Proposed","Reliability","P3206-1) Construct a new East 345 & 138 kV substation\n2) Install a new 345/138 kV transformer at East\n3) Loop Edgewater-South Fond du Lac, Edgewater-Cedarsauk, Sheboygan Energy Center-Granville \n    345 kV lines into East\n4) Loop the South Sheboygan Falls-Mullet River 138 kV line into East 138 kV\n5) Construct a new 138 kV line from East to Plymouth #4\n6) Construct a new 138 kV line from Plymouth #4 to Howards Grove\n7) Construct a new 138 kV line from Howards Grove to Erdman\n8) Convert the existing Forest Junction-Howards Grove-Plymouth #4 138 kV line and the \n    northern portion of the existing Plymouth #4-Holland 138 kV line to 345 kV\n9) Terminate the not-converted Holland 138 kV line at East 138 kV\n10) Terminate the southern end of the converted 345 kV line at East  \n11) Construct a new North 345 kV substation\n12) Loop the converted 345 kV line into North 345 kV substation\n13) Loop the Point Beach-Forest Juction, Point Beach-Sheboygan Energy Center 345 kV lines into North\n14) Uprate East-Cedarsauk 345 kV line to 960 MVA for SN/SE"]
["MISO","IL",349730,"7FARGO",349740,"7MAPLE",1,345,20,null,null,null,null,null,null,"2016-12-01","Planned","Reliability","P2472-Tap existing 345kV line from Duck Creek to Tazewell and create new Maple Ridge Substation ($6.5M)"]
["MISO","WI",693668,"SPG",699829,"CARDINAL",1,345,28,null,null,null,null,null,null,"2020-06-01","Proposed","Reliability","P2845-Construct a new Spring Green-Cardinal 345kV line"]
["MISO","WI",698849,"PLS",270941,"ZION",1,345,11.44,null,null,null,null,null,null,"2011-06-01","Proposed","Reliability","P3188-Replace Zion wave trap to increase line rating"]
["MISO","IA",635200,"RAUN",652564,"SIOUXCY3",2,345,23,null,null,null,null,null,null,"2014-06-01","Proposed","Reliability","P2939-Construct a 23 mile 345 kV line between the Raun and Sioux City Substations"]
["MISO","WI",601044,"NLAX",699818,"NMA",1,345,136.33099999999999,null,null,null,null,null,null,"2018-12-31","Proposed","Multi Value","P3127-Construct a new North La Crosse-North Madison 345kV line"]
["MISO","WI",699119,"ROE",699829,"CARDINAL",1,345,32.14,null,null,null,null,null,null,"2013-06-01","Proposed","Reliability","P356-Construct a new 345/138 kV substation at Cardinal (next to the existing West Middleton sub), install a 345/138 kV 500 MVA transformer at Cardinal, construct 47.9 miles overhead 345 kV line from Albion to Cardinal/West Middleton, modifications to the existing West Middleton substation, construct a new Albion 345 kV switching station.  Facility costs listed in the facility table are for the southern route."]
["MISO","IL",348774,"7BALDWIN",345669,"7RUSH",1,345,26,null,null,null,null,null,null,"2010-06-01","Planned","Other","P150-Establish a new Prairie State 345 kV switchyard including a 6-position breaker and ½ bus arrangement to accommodate 2 generating units and 4-345 kV outlet lines with 9-345 kV circuit breakers.  Tap the existing Baldwin-Stallings 345 kV line 4531 \"in and out\" and build 7.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  Tap the existing Baldwin-Mt. Vernon 345 kV line 4541 \"in and out\" and build 1.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  \n\nAt the Baldwin 345 kV switchyard, replace 9-345 kV circuit breakers that would be overstressed as a result of the Prairie State development.  Also install 3-345 kV circuit breakers for a new Baldwin-Rush Island 345 kV line and a new connection for the Baldwin 345/138 kV transformer.  Build a new 26 mile 345 kV 3000 A summer emergency capability line from Baldwin to Rush Island."]
["MISO","IL",348778,"7STALLINGS",348773,"7PR",1,345,7.5,null,null,null,null,null,null,"2012-11-01","Planned","Other","P150-Establish a new Prairie State 345 kV switchyard including a 6-position breaker and ½ bus arrangement to accommodate 2 generating units and 4-345 kV outlet lines with 9-345 kV circuit breakers.  Tap the existing Baldwin-Stallings 345 kV line 4531 \"in and out\" and build 7.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  Tap the existing Baldwin-Mt. Vernon 345 kV line 4541 \"in and out\" and build 1.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  \n\nAt the Baldwin 345 kV switchyard, replace 9-345 kV circuit breakers that would be overstressed as a result of the Prairie State development.  Also install 3-345 kV circuit breakers for a new Baldwin-Rush Island 345 kV line and a new connection for the Baldwin 345/138 kV transformer.  Build a new 26 mile 345 kV 3000 A summer emergency capability line from Baldwin to Rush Island."]
["MISO","IL",348827,"7W",348773,"7PR",1,345,1.5,null,null,null,null,null,null,"2010-06-01","Planned","Other","P150-Establish a new Prairie State 345 kV switchyard including a 6-position breaker and ½ bus arrangement to accommodate 2 generating units and 4-345 kV outlet lines with 9-345 kV circuit breakers.  Tap the existing Baldwin-Stallings 345 kV line 4531 \"in and out\" and build 7.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  Tap the existing Baldwin-Mt. Vernon 345 kV line 4541 \"in and out\" and build 1.5 miles of double-circuit 3000 A summer emergency capability line to the switchyard.  \n\nAt the Baldwin 345 kV switchyard, replace 9-345 kV circuit breakers that would be overstressed as a result of the Prairie State development.  Also install 3-345 kV circuit breakers for a new Baldwin-Rush Island 345 kV line and a new connection for the Baldwin 345/138 kV transformer.  Build a new 26 mile 345 kV 3000 A summer emergency capability line from Baldwin to Rush Island."]
["MISO","MN",608626,"BOSWELL4",620447,"CASS",1,230,68,null,null,null,null,null,null,"2011-12-31","Planned","Reliability","P279-Boswell - Wilton 230 ckt 1, Sum rate 495, \nAddition of a 187 MVA 230/115 kV transformer at Cass Lake"]
["MISO","MN",601046,"ALEXSS3",601047,"WAITEPK3",1,345,55,null,null,null,null,null,null,"2013-07-01","Planned","Reliability","P286-Maple River- AlexandriaSS - Waite Park - Monticello 345 ckt 1, Sum rate 2085"]
["MISO","MN/ND",657792,"MAPLE",601046,"ALEXSS3",1,345,135,null,null,null,null,null,null,"2015-07-01","Planned","Reliability","P286-Maple River- AlexandriaSS - Waite Park - Monticello 345 ckt 1, Sum rate 2085"]
["MISO","MN",601047,"WAITEPK3",601010,"MNTCELO3",1,345,35,null,null,null,null,null,null,"2011-12-01","Planned","Reliability","P286-Maple River- AlexandriaSS - Waite Park - Monticello 345 ckt 1, Sum rate 2085"]
["MISO","MN",601051,"HMPT",601039,"NROC",1,345,36,null,null,null,null,null,null,"2015-09-30","Planned","Reliability","P1024-Construct Hampton Corner-North Rochester-Chester-North LaCrosse 345 kV line, North Rochester - N. Hills 161 kV line, North Rochester-Chester 161 kV line,  Hampton Corner 345/161 transformer, North Rochester 354/161 transformer, North LaCrosse 345/161 transformer"]
["MISO","MN",601039,"NROC",601044,"NLAX",1,345,82,null,null,null,null,null,null,"2014-03-31","Planned","Reliability","P1024-Construct Hampton Corner-North Rochester-Chester-North LaCrosse 345 kV line, North Rochester - N. Hills 161 kV line, North Rochester-Chester 161 kV line,  Hampton Corner 345/161 transformer, North Rochester 354/161 transformer, North LaCrosse 345/161 transformer"]
["MISO","SD/MN",601031,"BRKNGCO3",601048,"LYON",1,345,48.1,null,null,null,null,null,null,"2015-04-27","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601048,"LYON",601049,"CEDAR",1,345,51.9,null,null,null,null,null,null,"2013-09-26","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601048,"LYON",601049,"CEDAR",1,345,51.9,null,null,null,null,null,null,"2013-09-27","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601049,"CEDAR",601050,"HELENA",2,345,62.2,null,null,null,null,null,null,"2013-11-22","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601049,"CEDAR",601050,"HELENA",1,345,62.2,null,null,null,null,null,null,"2013-11-22","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601050,"HELENA",601052,"LKMARION3",2,345,26.6,null,null,null,null,null,null,"2014-04-01","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601052,"LKMARION3",601051,"HMPT",1,345,18.5,null,null,null,null,null,null,"2014-06-23","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601048,"LYON",601054,"HAZEL",1,345,23.5,null,null,null,null,null,null,"2015-03-13","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601054,"HAZEL",602008,"MINVALT4",1,230,6,null,null,null,null,null,null,"2015-03-13","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","MN",601052,"LKMARION3",601051,"HMPT",1,345,18.5,null,null,null,null,null,null,"2014-06-23","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","SD/MN",601031,"BRKNGCO3",601048,"LYON",1,345,48.1,null,null,null,null,null,null,"2015-04-27","Proposed","Multi Value","P1203-Brookings Cty-Lyon Cty-Cedar Mountain-Helena-Lk Marion-Hampton Corner (Double Ckt 345 kV); Lyon Cty-Hazel (Double Ckt 345 kV); Hazel-Minnesota Valley (Double Ckt 345 kV, initially operate at 230 kV); Cedar Mountain-Franklin (Single Ckt 115 kV)"]
["MISO","IN",253620,"10ABB345",249510,"08GIBSON",1,345,40,null,null,null,null,null,null,"2011-05-31","Planned","Reliability","P1257-New 345 kV transmission line Gibson (Cinergy) to AB Brown (Vectren) to Reid (BREC)"]
["MISO","IN/KY",253620,"10ABB345",340562,"7REID",1,345,24,null,null,null,null,null,null,"2011-10-31","Planned","Reliability","P1257-New 345 kV transmission line Gibson (Cinergy) to AB Brown (Vectren) to Reid (BREC)"]
["MISO","IA",631140,"SALEM",631139,"HAZLTON3",1,345,81,null,null,null,null,null,null,"2011-12-31","Planned","Other","P1340-Build a new Hazleton - Salem 345 kV line.  Expand the Hazleton 345kV bus to a 5 position ring and expand the Salem 345kV ring to allow for a 2nd Salem 345/161 kV 448 MVA transformer. (option 1)  The route will follow the existing Hazleton-Dundee-Liberty-Lore 161kV route."]
["MISO","IN",243207,"05GRNTWN",700555,"MEADOW",1,765,117,null,null,null,null,null,null,"2018-09-01","Proposed","Multi Value","P2202-part of 765 kV loop completion in Indiana"]
["MISO","IN",243210,"05SULLVA",700555,"MEADOW",1,765,72,null,null,null,null,null,null,"2018-09-01","Proposed","Multi Value","P2201-part of 765 kV loop completion in Indiana"]
["MISO","MI",265076,"19WYATT",265077,"19W-S-G",1,345,28,null,null,null,null,null,null,"2015-12-31","Planned","Multi Value","P3168-Double circuit 345 kV transmission for integration of wind resources"]
["MISO","MI",264706,"19GRNEC",265077,"19W-S-G",2,345,22,null,null,null,null,null,null,"2015-12-31","Planned","Multi Value","P3168-Double circuit 345 kV transmission for integration of wind resources"]
["MISO","MI",264706,"19GRNEC",264746,"19STOGA",2,345,16,null,null,null,null,null,null,"2015-12-31","Planned","Multi Value","P3168-Double circuit 345 kV transmission for integration of wind resources"]
["MISO","IA",631139,"HAZLTON3",636000,"WEBSTER3",2,345,112,null,null,null,null,null,null,"2015-12-31","Proposed","Multi Value","P3211-345 kV line for Iowa wind outlet"]
["MISO","IA,MN",631144,"Mitchel Co",631138,"Lakefield Junction",2,345,86,null,null,null,null,null,null,"2015-12-31","Proposed","Reliability","P1746-345 kV line for Minnesota wind outlet and Iowa wind collection"]
["MISO","IA,MO",631143,"OTTUMWA3",344002,"WAdairTp",1,345,57.75,null,null,null,null,null,null,"2014-06-01","Proposed","Multi Value","P2248-345 kV line for MO wind collection and increased North-South capability"]
["MISO","MO",300039,"FAIRPT",344002,"WAdairTp",1,345,101.13,null,null,null,null,null,null,"2014-06-01","Proposed","Multi Value","P2248-345 kV line for MO wind collection and increased North-South capability"]
["MISO","MO",300049,"7THOMHL",344002,"WAdairTp",1,345,47.25,null,null,null,null,null,null,"2014-06-01","Proposed","Multi Value","P2248-345 kV line for MO wind collection and increased North-South capability"]
["MISO","IL",347679,"Meredosia",348060,"SEQuincy",1,345,45,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P3017-345 kV line for IL wind collection and increased East-West energy transfer"]
["MISO","MO,IL",345435,"7PALM TAP",348060,"SEQuincy",1,345,15,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P3017-345 kV line for IL wind collection and increased East-West energy transfer"]
["MISO","IL",347679,"Meredosia",347962,"Pawnee",1,345,63,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P2236-345 kV line for IL wind collection and increased East-West energy transfer"]
["MISO","IL",347962,"7PAWNEE",347945,"Pana",1,345,22,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P2236-345 kV line for IL wind collection and increased East-West energy transfer"]
["MISO","OH",238569,"02BEAVER",238654,"02DAV-BE",2,345,19,null,null,null,null,null,null,"2013-06-01","Proposed","Multi Value","P2260-345 kV line for interconnection of wind resources"]
["MISO","SD",601031,"BRKNGCO3",620313,"BIGSTON3",1,345,35,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P2221-345 kV transmission for collection of wind energy"]
["MISO","MI",265082,"Arrowhead",265083,"Cosmo Tap",1,345,15,null,null,null,null,null,null,"2015-12-31","Planned","Multi Value","P3168-Double circuit 345 kV transmission for integration of wind resources"]
["MISO","IA",636000,"WEBSTER3",637422,"Burt",1,345,15,null,null,null,null,null,null,"2015-12-31","Proposed","Multi Value","P3205-345 kV line for collection of wind energy"]
["MISO","IA",637422,"Burt",637526,"Osgood",1,345,14,null,null,null,null,null,null,"2015-12-31","Proposed","Multi Value","P3205-345 kV line for collection of wind energy"]
["MISO","IA",637526,"Osgood",637568,"Wisdom",1,345,14,null,null,null,null,null,null,"2015-12-31","Proposed","Multi Value","P3205-345 kV line for collection of wind energy"]
["MISO","IA",635368,"SHELDON",637568,"Wisdom",1,345,95,null,null,null,null,null,null,"2015-12-31","Proposed","Multi Value","P3205-345 kV line for collection of wind energy"]
["MISO","IL",347288,"7IPAVA",347679,"Meredosia",1,345,35,null,null,null,null,null,null,"2015-08-01","Proposed","Multi Value","P3017-345 kV line for IL wind collection and increased East-West energy transfer"]
["MISO","MO",344002,"WAdairTp",345436,"7PALMYRA",1,345,64,null,null,null,null,null,null,"2018-06-01","Proposed","Multi Value","P3170-345 kV line for MO wind collection and increased North-South capability"]
["MISO","MN,WI",631180,"DUBUQUE",693668,"SPG",1,345,75.13,null,null,null,null,null,null,"2017-06-03","Proposed","Multi Value","P2832-Construct a new Dubuque Co-Spring Green 345kV line"]
["MISO","MN",620447,"CASS LK4",608626,"BOSWELL4",1,230,85,null,null,null,null,null,null,"2011-12-31","Proposed","Reliability","P279-Boswell - Wilton 230 ckt 1, Sum rate 495, \nAddition of a 187 MVA 230/115 kV transformer at Cass Lake"]
["MISO","WI",699002,"COUNCIL CK",699239,"COC 138",1,161," ",null,null,null,null,null,null,"2013-06-01","Proposed","Other","P574-Monroe County - Council Creek 161 kV line, Council Creek 161/138 kV transformer; Council Creek-Petenwell uprate 138 kV"]
["MISO","WI",699829,"Cardinal",699820,"345/138kV Xfmr",1,345,0,null,null,null,null,null,null,"2013-06-01","Planned","Reliability","Construct a new 345/138 kV substation at Cardinal (next to the existing West Middleton sub), install a 345/138 kV 500 MVA transformer at Cardinal, construct 47.9 miles overhead 345 kV line from Albion to Cardinal/West Middleton, modifications to the existing West Middleton substation, construct a new Albion 345 kV switching station.  Facility costs listed in the facility table are for the southern route."]
["MISO","MI",256509,"18WEEDLK",256000,"18ARGNTA",1,345,10,null,null,null,null,null,null,"2013-06-01","Proposed","Reliability","P662-Loop the 345kV Argenta - Robinson Park 345kV circuit into a new 345/138kV EHV substation called Weeds Lake.  Build 4 new (approximately 6 miles) 138kV circuits to loop the two Argenta-Milham 138kV lines into the substation."]
["MISO","IN",249525,"08WESTWD",249874,"08WESTWD",1,345," ",null,null,null,null,null,null,"2015-06-01","Planned","Reliability","P841-Replace 1600A 138kV breaker with 3000A to allow full xfr rating."]
["MISO","MN",620184,"WINGR Y2",620238,"WINGER",1,230," ",null,null,null,null,null,null,"2011-12-31","Proposed","Reliability","P971-Winger 230/115 kV Transformer upgrade"]
["MISO","MO",345543,"5ENONTP1",300597,"5ENON",1,161,1,null,null,null,null,null,null,"2011-06-01","Planned","Reliability","P1238-Extend 1 mile of 161 kV to AECI Enon Substation"]
["MISO","IN",249608,"08CAYUGA",249615,"08FRNKFT",1,230,0,null,null,null,null,null,null,"2013-06-01","Planned","Reliability","P1244-Upgrade wave traps at Cayuga and Frankfort to increase line rating to 797 MVA."]
["MISO","IN",249619,"08GRNTWN",249627,"08PER SE",1,230,0,null,null,null,null,null,null,"2011-06-01","Planned","Reliability","P1247-Upgrade Greentown to Peru SE 230kV line to 100C operating temperature."]
["MISO","IN",249626,"08NOBLSV",249618,"08GEIST",1,230,0,null,null,null,null,null,null,"2011-06-01","Planned","Reliability","P1253-Replace 800A wave trap with a 2000A wave trap. Increase line rating for Noblesville to Geist 230kV line."]
["MISO","IN",253620,"10ABB345",249510,"08GIBSON",1,345,0,null,null,null,null,null,null,"2011-05-31","Planned","Reliability","P1257-New 345 kV transmission line Gibson (Cinergy) to AB Brown (Vectren) to Reid (BREC)"]
["MISO","IN",249530,"08EDWDSP",251903,"08EDWST",1,345,0,null,null,null,null,null,null,"2010-03-15","Under Construction","Reliability","P1263-Edwardsport 420 MW: The Generating Facility will be located near the Interconnection Customer’s existing Edwardsport Generating Station site which has three existing units 6, 7 and 8 that shall be retired before the Generating Facility provided by this LG"]
["MISO","IN",249520,"08SPEED",249850,"08SPEED",1,345,0,null,null,null,null,null,null,"2013-06-01","Planned","Reliability","P1264-Replace existing 345/138 transformer at Speed with a new transformer rated at 3,000A or higher."]
["MISO","IA",631139,"HAZLTON3",631050,"HAZLTON5",1,345,0,null,null,null,null,null,null,"2010-12-31","Planned","Reliability","P1288-Replace Hazleton 345/161 kV transformer #1 with 448 MVA unit"]
["MISO","MI",264883,"19B3N PS",264536,"19BUNCE1",1,220,0,null,null,null,null,null,null,"2010-09-30","Planned","Other","P1308-Returns the Bunce Creek to Scott 220 kV circuit to service, and replaces the Phase Angle Regulator with 2 new phase angle regulating transformers in series"]
["MISO","IN",248693,"07NAPOL1",248470,"07DCTRSS",1,161,25,null,null,null,null,null,null,"2008-03-01","Planned","Other","P1321-161kV Transmission from  Napoloen to DCSS, 30 MVAR Cap"]
["MISO","IA",631139,"HAZLTON3",631140,"SALEM  3",1,345,0,null,null,null,null,null,null,"2011-06-01","Planned","Other","P1340-Build a new Hazleton - Salem 345 kV line.  Expand the Hazleton 345kV bus to a 5 position ring and expand the Salem 345kV ring to allow for a 2nd Salem 345/161 kV 448 MVA transformer. (option 1)  The route will follow the existing Hazleton-Dundee-Liberty-L"]
["MISO","IA",631146,"LWSFLDS7",631147,"LWSFLDS5",1,161,0,null,null,null,null,null,null,"2012-12-31","Planned","Reliability","P1342-Build a new 161 kV substation Lewis Fields to be tapped to the 115 kV line Swamp Fox - Coggon at 5% distance via a new 161/115 kV transformer. Also build a new 161 kV line from Hiawatha to Lewis Fields"]
["MISO","IA",631148,"MORGANV3",631149,"MORGANV5",1,345,7.9,null,null,null,null,null,null,"2013-06-01","Proposed","Other","P1344-Build a new 345 kV Morgan Valley (Beverly) Tap substation and tapped to 345 kV line Arnold -Tiffin at 40% distance away from Arnold. Add a new 335 MVA 345/161 kV transformer and build a new 161 kV line connecting the new substation to Beverly 161 kV bus. "]
["MISO","IA",631141,"ROCK CK3",631140,"SALEM  3",1,345,0,null,null,null,null,null,null,"2011-06-01","Planned","Reliability","P1345-Replace the limiting facility of CTs and conductor inside the substations for 345 kV line Quad Cities-Rock Creek-Salem so the line rating can be raised to the same as conductor rating between substations"]
["MISO","ND",661053,"HESKET24",661054,"HESKET27",1,230,0,null,null,null,null,null,null,"2014-12-31","Planned","Reliability","P1355-Heskett - Additional 230/115 kV Switchyard  230 115 Switchyard in parallel w/ existing Heskett switchyard and Cap Bank"]
["MISO","IN",249630,"08STAUTN",249633,"08WAB",1,230,0,null,null,null,null,null,null,"2011-06-01","Planned","Other","P1514-Uprate Wabash River to Staunton 23002 to 100C summer operating temperature and 80C winter (559MVA)."]
["MISO","IN",249621,"08KOK HP",249635,"08WEBSTE",null,230,0,null,null,null,null,null,null,"2012-06-01","Planned","Other","P1561-Retire existing 1600A circuit switcher and complete the Webster St ring in order to utilize the full capacity of the bundled 477 ACSS wire on the 23016 line."]
["MISO","IN",249889,"08QUALTC",249518,"08QUALTC",1,345,0,null,null,null,null,null,null,"2013-06-01","Planned","Reliability","P1568-Qualitech Sub- Install one 345/138kv, 300Mva Xtr and 2-345kv Bkrs and 1-138kv Bkr to provide second 138kv source to proposed Hendricks Co 138kv system"]
["MISO","OH",238615,"02CHAMBR",238941,"02MANSFD",1,345,2,null,null,null,null,null,null,"2014-06-01","Proposed","Other","P1607-Loop the Chamberlin - Mansfield 345 kV Line in and out of Hanna Substation creating a Chamberlin - Hanna and a Hanna - Mansfield 345 kV Line."]
["MISO","PA",239280,"02CRNBRY",239281,"02CRNBRY",2,500,0,null,null,null,null,null,null,"2012-06-01","Planned","Reliability","P1612-Construct a 500/138kV Sub with four exits in the Cranberry/Adams Township area."]
["MISO","MN",631041,"LAKEFLD5",631040,"HRN LK 5",1,161,17,null,null,null,null,null,null,"2012-12-31","Planned","Reliability","P1618-Rebuild Heron Lake-Lakefield 161kV line, sum rate 446 MVA "]
["MISO","IA",631115,"OTTUMWA5",null,null,null,161,0,null,null,null,null,null,null,"2011-05-30","Planned","Reliability","P1641-Install a 161kV 50 MVAR cap bank at the Ottumwa Generating Station."]
["MISO","IA",631070,"ANITA  5",null,null,null,161,0,null,null,null,null,null,null,"2013-12-31","Proposed","Reliability","P1643-Install a 161kV 24 MVAR cap bank at the Anita substation."]
["MISO","IA",631074,"GR JCT 5",null,null,null,161,0,null,null,null,null,null,null,"2013-12-31","Proposed","Reliability","P1644-Install a 161kV 24 MVAR cap bank at the Grand Junction substation."]
["MISO","WI",602025,"Monroe Co",699002,"Council Ck",1,161,17.3,null,null,null,null,null,null,"2013-06-01","Planned","Reliability","Monroe County - Council Creek 161 kV line, Council Creek 161/138 kV transformer; Council Creek-Petenwell uprate 138 kV"]
["MISO","IA",631096,"GR MND 5",631098,"MQOKETA5",1,161,14.5,null,null,null,null,null,null,"2016-12-31","Planned","Reliability","P1744-Reconductor 161kV from Maquoketa to Grand Mound (old East Calamus-Maquoketa 161kV line)"]
["MISO","IA",631048,"EMERY  5",631047,"LIME CK5",1,161,1,null,null,null,null,null,null,"2010-12-31","Planned","Other","P1754-Rebuild a portion of the Emery-Lime Creek 161kV line (about 1 mile)"]
["MISO","MI",256022,"18ROSVLT",256024,"18TALLMG",1,345,0,null,null,null,null,null,null,"2010-12-31","Planned","Reliability","P1799-Remove the SAG limit on:  Roosevelt - Tallmadge"]
["MISO","MI",256000,"18ARGNTA",256019,"18PALISD",1,345,0,null,null,null,null,null,null,"2010-06-01","Planned","Reliability","P1828-Remove the SAG limit on Argenta-Palisades 345kV ckt 1& 2. Upgrade terminal equipment at both substations."]
["MISO","MI",264580,"19JEWEL",264635,"19PONTC",1,345,0,null,null,null,null,null,null,"2011-12-01","Proposed","Reliability","P1856-Cut the Pontiac section of the Belle River-Greenwood-Pontiac 345kV circuit into and out of Jewell station.  Utilize an existing unused side of 345kV tower for one of the circuits into Jewell, and relocate the Jewell-Spokane 230kV circuit"]
["MISO","OH",238654,"02DAV-BE"," ",null,3,345,0,null,null,null,null,null,null,"2010-12-17","Planned","Reliability","P1909-Reconfigure the Davis Besse switch yard by extending J and K buses and adding 345kV breakers"]
["MISO","WI",699630,"KEWAUNEE",699620,"KEWAUNEE",2,345,0,null,null,null,null,null,null,"2011-05-01","Proposed","Reliability","P1950-Reconfigure Kewaunee 345/138 kV switchyard and install a 2nd Kewaunee 345-138 kV transformer of 500 MVA."]
["MISO","MN",601015,"BLUE LK3",601004,"WILMART3",1,345,0,null,null,null,null,null,null,"2010-12-01","Planned","Multi Value","P1956-This project is to increase the capacity of the 345 kV line between Wilmarth and Blue Lake. Phase raise the line to allow for a normal 100 degree C operation.  Allow for a 10% emergency loading using the new 4 ft/sec wind speed rating."]
["MISO","IN",253620,"10ABB345",249510,"08GIBSON",1,345,0,null,null,null,null,null,null,"2011-05-31","Planned","Reliability","P1970-New 448MVA 345/138kV transformer in addition to the Gibson-AB Brown-Reid 345kV line."]
["MISO","IN",249508,"08DRESSR",249721,"08DRESSR",3,345,0,null,null,null,null,null,null,"2010-06-01","Planned","Reliability","P2050-Add a 3rd 345/138kV transformer at Dresser Sub"]
["MISO","IN",254529,"16PETE",254638,"16PETE",2,345,0,null,null,null,null,null,null,"2012-06-01","Planned","Reliability","P2053-Replace and upgrade existing East and West 345/138kV autotransformer at Petersburg Substation. Add 345kV breaker."]
["MISO","MO",344648,"7GRAYSUM1",344650,"4GRAY",2,345,0,null,null,null,null,null,null,"2010-12-01","Planned","Reliability","P2061-Install a 345 kV six position ring bus making Labadie -  Tyson 1 & 2 345 kV lines and add a second 560 MVA 345/138 kV transformer."]
["MISO","IL",347820,"6N COULTR",348816,"4N",1,230,0,null,null,null,null,null,null,"2010-06-01","Proposed","Reliability","P2063-\"Replace existing 140 MVA, 230/138 kV transformer with a 225 MVA unit.  Install new 230kV circuit switcher and disconnect switch.\nInstall new potential transformers for station power and upgrade the wave trap on the Coulterville-Tilden 138 kV line \n      "]
["MISO","IL",348856,"7LATHAM",348851,"7OREANA",1,345,8.5,null,null,null,null,null,null,"2014-12-01","Planned","Reliability","P2068-Convert Oreana 345 kV Bus to 6-Position Ring Bus with 3000 A Capability; Construct 8.5 miles of 345 kV line (2-954 kcmil ACSR conductor or equivalent capability) from Oreana Substation to 345 kV Line 4571 tap to Latham Substation.  3-345 kV PCB's at Orean"]
["MISO","IL",349265,"S.BLOOMGTN",348874,"4S",1,345,0,null,null,null,null,null,null,"2014-12-01","Planned","Reliability","P2069-South Bloomington Area 345/138 kV Substation - Install 345/138 kV, 560 MVA Transformer.  Extend new 345 kV line approximately 5 miles from Brokaw Substation to South Bloomington Substation.  Install 1-138 kV PCB at South Bloomington Substation, and 2-345 "]
["MISO","OH",249575,"08TERMNL",250117,"08TRMNL1",1,345,0,null,null,null,null,null,null,"2009-12-31","Under Construction","Other","P2141-Terminal Substation - replace 138kv bank breaker and moving from line terminal 1782 over to main 138kv bus #1; replacing: 345kv(4514) wave trap, 138kv(1782 and 7481) wave traps"]
["MISO","OH",239313,"02FULTON",238738,"02FULTON",1,345,0,null,null,null,null,null,null,"2017-06-01","Proposed","Reliability","P2250-Construct Fulton Substation near the crossing point of the Allen Junction-Midway 345kV and Delta-Swanton 138kV lines, loop both lines into the new 345/138kV ring bus substation, install one 345/138kV transformer.\n"]
["MISO","IA",631116,"BRDGPRT5",631104,"EIC",1,161,0,null,null,null,null,null,null,"2010-12-31","Under Construction","Reliability","P2359-Upgrade the Bridgeport 161kV sub & the EIC sub.  These upgrades combined with the Tri-County upgrades will allow for the Bridgeport 69kV sub to be retired.  The Bridgeport 69kV sub needs to be retired to allow for the plant to expand."]
["MISO","IA",631052,"LANSINGW",681523,"GENOA  5",1,161,0,null,null,null,null,null,null,"2010-12-31","Planned","Reliability","P2365-Upgrade the terminal limits & relaying on the Lansing-Genoa 161kV."]
["MISO","MI",256500,"18MRPHYT",256499,"18MURPHY",4,345,0,null,null,null,null,null,null,"2011-06-01","Planned","Reliability","P2500-Install a second 345/138kV transformer at Murphy substation"]
["MISO","WI",698863,"BLUMND3",698865,"BLUMND6",1,230,0,null,null,null,null,null,null,"2011-11-30","Proposed","Reliability","P2819-Replace Bluemound 230/138kV transformer T3 with a 400 MVA unit"]
["MISO","WI",699262,"BLUMND1",699263,"BLUMND4",1,230,0,null,null,null,null,null,null,"2012-05-31","Proposed","Reliability","P2820-Replace Bluemound 230/138kV transformer T1 with a 400 MVA unit"]
["MISO","IL",346895,"7COFFEEN",346886,"7COFFEN N",2,345,0,null,null,null,null,null,null,"2010-12-01","Planned","Multi Value","P2829-Install a second 345 kV bus tie between Coffeen and Coffeen N ring busses; add a ring bus position at each station. Replace Coffeen N. wave trap and Ramsey E. switch to increase line rating from 956 MVA to 1195 MVA."]
["MISO","IN",249626,"08NOBLSV",249618,"08GEIST",1,230,0.6,null,null,null,null,null,null,"2011-12-01","Planned","Other","P2874-Relocate section of 23007 between Noblseville and Giest to new RoW around expanding mine operation - approx. 0.6 mile of added line length"]
["MISO","IN",254529,"16PETE",254521,"16FRANCS",1,345,111.42,null,null,null,null,null,null,"2013-06-01","Proposed","Reliability","P2897-Increase line rating from 956 to 1195 MVA"]
["MISO","IN",254523,"16GUION",249529,"08WHITST",1,345,11.14,null,null,null,null,null,null,"2015-06-01","Proposed","Reliability","P2899-Increase line rating from 956 to 1195 MVA"]
["MISO","IL",636600,"SB 39  3",636601,"SB 39  5",2,345,0,null,null,null,null,null,null,"2014-06-01","Proposed","Reliability","P2937-Add a second 345-161 kV xfmr.  Expand 345 kV and 161 kV buses."]
["MISO","IL",636600,"SB 39  3",636605,"MECCORD3",1,345,15.5,null,null,null,null,null,null,"2014-06-01","Proposed","Reliability","P2938-Change out structures to increase rating."]
["MISO","MO",300617,"5SCRUGG",344028,"5APCH",1,161,0,null,null,null,null,null,null,"2011-06-01","Planned","Other","P2970-Apache Flats 161 kV Substation - Install 1-161 kV, 2000 A PCB and necessary metering and relaying to provide a delivery point for Associated Electric's Scruggs 161-69 kV Substation."]
["MISO","IA",636199,"BLACKHAWK",636200,"BLKHAWK5",1,345,null,null,null,null,null,null,null,"2018-12-31","Proposed","Multi Value","P3211-Add a Blackhawk 345/161kv Xfmr to the Hazelton-Webster 345 kV line"," "]

{"sheet":"NBSO","index":14,"n_rows":5,"n_cols":19,"rows_kept":5,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]

{"sheet":"NY-ISO","index":15,"n_rows":19,"n_cols":19,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["NYISO","NJ/NY",217100,"Bergen 230 kV (NJ)",128749,"Hudson Converter",23,"230/345",null,null,null,null,null,null,null,2011,"Planned",null," AC/DC/AC converter"]
["NYISO","NJ/NY",128749,"Hudson Converter",126304,"West 49th St 345kV ",1,345,null,null,null,null,null,null,null,2011,"Planned",null,"345 kV AC cable"]
["NYISO","NY",126281,"E. Fishkill",125022,"E. Fishkill",2,"345/115",null,null,null,null,null,null,null,2010,"Planned",null,"Transformer #2 (Standby)"]
["NYISO","NY",126298,"Sprain Brook",126847,"Academy",1,345,null,null,null,null,null,null,null,2011,"Planned",null," 2000 CU"]
["NYISO","NY",126277,"Farragut",126272,"East 13th Street",1,345,null,null,null,null,null,null,null,2010,"Planned",null,"Refrigeration Cooling"]
["NYISO","NY",126277,"Farragut",126273,"East 13th Street",1,345,null,null,null,null,null,null,null,2010,"Planned",null,"Refrigeration Cooling"]
["NYISO","NY",147845,"Willis 1",147980,"Patnode",1,230,null,null,null,null,null,null,null,2011,"Planned",null,"1-795 ACSR"]
["NYISO","NY",147980,"Patnode",147859,"Duley",1,230,null,null,null,null,null,null,null,2011,"Planned",null,"1-795 ACSR"]
["NYISO","NY",131157,"Clarks Corners",130824,"Clarks Corners",1,"345/115",null,null,null,null,null,null,null,2010,"Under Construction",null,"Transformer"]
["NYISO","NY",131157,"Clarks Corners",130824,"Clarks Corners",2,"345/115",null,null,null,null,null,null,null,2010,"Under Construction",null,"Transformer"]
["NYISO","NY",130761,"Avoca",131154,"Stony Ridge",1,230,null,null,null,null,null,null,null,2011,"Planned",null,"1033.5 ACSR"]
["NYISO","NY",131154,"Stony Ridge",130763,"Hillside",1,230,null,null,null,null,null,null,null,2011,"Planned",null,"1033.5 ACSR"]
["NYISO","NY",131154,"Stony Ridge",131155,"Stony Ridge",1,"230/115",null,null,null,null,null,null,null,2011,"Planned",null,"Transformer"]
["NYISO","NY",126277,"Farragut",126275,"East 13th Street",1,345,null,null,null,null,null,null,null,2016,"Planned",null,"Reconductoring"]

{"sheet":"PJM","index":16,"n_rows":11,"n_cols":13,"rows_kept":11,"cut":false,"hidden":false,"merged":[[3,7,4,7],[3,8,4,8],[3,9,4,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[0,0,0,12],[1,0,2,12],[3,0,4,0],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,4,6]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name"]
["PJM","PA, WV, VA",235111,"502 Jct 500KV",314913,"Loudoun 500KV",1,"500KV",215,"2011-06-01","Under Construction ","Reliability","TRAIL Project"]
["PJM","NJ",200002,"Branchburg 500KV",200096,"Hudson 500KV",1,"500KV",58,"2013-06-01","Planned","Reliability","Branchburg-Hudson 500 KV line"]
["PJM","VA",314902,"Carson 500KV",314928,"Suffolk 500KV",1,"500KV",52,"2011-06-01","Under Construction ","Reliability","Carson-Suffolk 500 KV line"]
["PJM","WV, VA, MD",242508,"John Amos 765KV",235636,"Kemptown 765KV",1,"765KV",275,"2015-06-01","Planned","Reliability","PATH Project"]
["PJM","VA, MD",314922,"Possum Point 500KV",200150,"VIENNA 500 KV",1,"500KV",130,"2017-06-01","Planned","Reliability","MAPP Project"]
["PJM","PA, NJ",200022,"Susquehanna 500KV",200094,"Roseland 500KV",1,"500KV",152,"2012-06-01","Planned","Reliability","Susquehanna-Roseland 500 KVLine "]

{"sheet":"POWERSOUTH","index":17,"n_rows":6,"n_cols":19,"rows_kept":6,"cut":false,"hidden":false,"merged":[[5,1,5,18],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,17,4,17],[3,18,4,18],[3,9,3,10],[3,11,3,14],[3,15,4,15],[3,16,4,16]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["PS","**NONE**"]

{"sheet":"PEC","index":18,"n_rows":13,"n_cols":20,"rows_kept":13,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Sum A","Sum B","Win A","Win B"]
["Progress Energy Carolinas","NC",304803,"6ASHEVL",304763,"6ENKA SW",1,230,11.75,"3-1272","ACSR",566,566,637,637,2010,"Under Construction","Reliability","115 to 230 kV Line Conversion & new 230/115 kV transformation"]
["Progress Energy Carolinas","NC",304378,"6RICHMON",304398,"6FB-WODR",1,230,70,"6-1590","ACSR",1195,1195,1195,1195,2011,"Under Construction","Reliability","Construct new 230 kV Line"]
["Progress Energy Carolinas","NC",304332,"6ASHEB",306152,"6PL GRDN",1,230,18.899999999999999,"6-1590","ACSR",1195,1195,1195,1195,2011,"Under Construction","Reliability","Construct new 230 kV Line"]
["Progress Energy Carolinas","NC",304348,"6RKH",304361,"6WESTEND",1,230,32,"6-1590","ACSR",1195,1195,1195,1195,2011,"Under Construction","Reliability","Construct new 230 kV Line"]
["Progress Energy Carolinas","NC",304205,"6CLINTON",304251,"6LEE",1,230,28,"3-1590","ACSR",615,615,691,691,2011,"Under Construction","Reliability","Construct new 230 kV Line & new 230/115 kV substation"]
["Progress Energy Carolinas","NC",304542,"6FOLKSTN","N/A","N/A","N/A",230,"N/A","N/A","N/A",224,224,224,224,2013,"Under Construction","Reliability","Construct 230/115 kV substation, loop in 230kV line"]
["Progress Energy Carolinas","NC",304009,"6HARRIS1",304159,"6RTP230",1,230,18,"6-1590","ACSR",1195,1195,1195,1195,2014,"Under Construction","Reliability","Construct new 230 kV Line","X"]
["Progress Energy Carolinas","NC",304451,"6PA-GRNV",304474,"6DUP KIN",1,230,30,"3-1590","ACSR",628,628,719,719,2017,"Planned","Reliability","Construct new 230 kV Line","X"]

{"sheet":"PEF","index":19,"n_rows":45,"n_cols":19,"rows_kept":45,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["PEF","FL",403701,"DISSTON",403704,"NORTHEAST","1",230,4.21,"1622 ACSS/TW (Pecos)  - > '07",null,936,996,1035,1085,2012,"Planned","Reliability","New line"]
["PEF","FL",403701,"DISSTON",403702,"FORTIETH STREET",1,230,3.5,"1622 ACSS/TW (Pecos)  - > '07",null,936,936,1035,1085,2014,"Planned","Reliability","New line"]
["PEF","FL",403832,"Morgan Road",408020,"DL MABRY (TECo)",1,230,8,"1622 ACSS/TW (Pecos)  - > '07",null,936,996,1035,1085,2011,"Under Construction","Reliability","New line"]
["PEF","FL",403832,"Morgan Road",403838,"ZEPHYRHILLS NORTH",1,230,23,"1622 ACSS/TW (Pecos)  - > '07",null,936,996,1035,1085,2013,"Under Construction","Reliability","New 230kV Tie-Line"]
["PEF","FL",402288,"Lake Tarpon",402913,"Kathleen",1,500,44,"2-2335","ACSR",2870,2870,2870,2870,2015,"Planned","Reliability","New line"]
["PEF","FL",402584,"MYRTLE LAKE",402585,"NORTH LONGWOOD","1",230,3.13,"954 KCM ACSR  (Cardinal)",null,492,604,574,659,2017,"Planned","Reliability","Line upgrade"]
["PEF","FL",402887,"HINES ENERGY COMPLEX",402891,"WEST LAKE WALES",2,230,21,"1622","ACSS/TWD",1007,1137,1142,1247,2011,"Under Construction","Reliability","New line"]
["PEF","FL",402891,"DUNDEE",402883,"INTERCESSION CITY",1,230,20,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2010,"Under Construction","Reliability","Line upgrade"]
["PEF","FL",402891,"LOUGHMAN (FUT)",402883,"INTERCESSION CITY",2,230,20,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2010,"Under Construction","Reliability","New 230kV Line"]
["PEF","FL",403516,"AMERICAN CEMENT; SECO",403517,"BUSHNELL EAST","1",230,9.5,"1622 ACSS/TW (Pecos)  - > '07",null,936,996,1035,1085,2020,"Planned","Reliability","New 230 kV Line"]
["PEF","FL",403518,"BROOKRIDGE",403519,"BROOKSVILLE WEST","1",230,3.32,"1590 KCM ACSR (Falcon)",null,677,813,789,902,2011,"Under Construction","Reliability","New 230kV Line"]
["PEF","FL",403518,"BROOKRIDGE",403532,"Lecanto","1",230,22.36,"1590 KCM ACSR (Falcon)",null,677,813,789,902,2012,"Under Construction","Reliability","New 230kV Line"]
["PEF","FL",403550,"Brookridge",403559,"Levy",1,500,42.400001525878899,"2-2335","ACSR",2870,2870,2870,2870,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403551,"Central Florida",403559,"Levy",1,500,60.900001525878899,"2-2335","ACSR",2890,2890,2890,2890,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",402163,"Camp lake",402160,"Hancock Road",31,230,5.4,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2017,"Planned","Reliability","Line upgrade"]
["PEF","FL",402068,"Haines Creek",403521,"CENTRAL FLORIDA",31,230,5.4,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2017,"Planned","Reliability","Line upgrade"]
["PEF","FL",403514,"Central Florida South",402163,"CampLake",31,230,19.239999999999998,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2017,"Planned","Reliability","Line upgrade"]
["PEF","FL",403514,"Central Florida South",402164,"Clermont East",31,230,4.88,"2627 ACSS/TW (Santee), Type 8",null,1195,1195,1195,1195,2017,"Planned","Reliability","Line upgrade"]
["PEF","FL",402272,"LK TARPN-B",402884,"KATHLEEN",31,230,44,"Bundled 954 ACSS/TW ",null,1195,1195,1195,1195,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403559,"LEVY        500.00",403561,"CFLA_SO500  500.00",31,500,null,"Triple Bundl 1590 ACSR",null,2870,2870,2870,2870,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403559,"LEVY        500.00",403562,"CITRUS500   500.00",31,500,null,"Triple Bundl 1590 ACSR",null,2870,2870,2870,2870,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403559,"LEVY        500.00",403562,"CITRUS500   500.00",32,500,null,"Triple Bundl 1590 ACSR",null,2870,2870,2870,2870,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403555,"CRYST RV    500.00",403559,"LEVY        500.00",31,500,null,"Triple Bundl 1590 ACSR",null,2598,2598,2598,2598,2017,"Planned","Reliability","New 500kV Line"]
["PEF","FL",403513,"CITRUS230   230.00",403523,"CRYST RE    230.00",31,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","New 230 kV Line"]
["PEF","FL",403513,"CITRUS230   230.00",403523,"CRYST RE    230.00",32,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","New 230 kV Line"]
["PEF","FL",403518,"BRKRIDGE    230.00",403519,"BRKSVL W    230.00",32,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","Loop into BrksvlWest"]
["PEF","FL",403518,"BRKRIDGE    230.00",403519,"BRKSVL W    230.00",33,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","Loop into BrksvlWest"]
["PEF","FL",403518,"BRKRIDGE    230.00",403522,"CR PLANT    230.00",32,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","Unloop the CREst sub from the existing CR-Brkrdge 230 kV line"]
["PEF","FL",403519,"BRKSVL W    230.00",403836,"HUDSN       230.00",32,230,null,"1590 ACSR",null,677,813,789,902,2017,"Planned","Reliability","Loop existing Brkrdge-Hudson 230 kV line into BrksvlWest"]
["PEF","FL",403527,"HOLDER      230.00",403533,"ROSSPRAI    230.00",32,230,null,"1590 ACSR","2000A Limited",677,797,789,797,2017,"Planned","Reliability","Loop Holder-CFL 230 kV line into RossPrairie substation"]
["PEF","FL",403518,"BRKRIDGE    230.00",403522,"CR PLANT    230.00",33,230,null,"954 ACSS/TW Bif",null,1195,1195,1195,1195,2017,"Planned","Reliability","New 230 kV line"]
["PEF","FL",403515,"ANDERSEN ",403521,"CENTRAL FLORIDA",31,230,null,"1590 ACSR",null,637,637,637,637,2017,"Planned","Reliability","New 230 kV line"]
["PEF","FL",403515,"ANDERSEN",403533,"ROSS PRAIRIE",31,230,null,"1590 ACSR",null,637,637,637,637,2017,"Planned","Reliability","New 230 kV line"]
["PEF","FL",402883,"INTERCESSION CITY 230.00",402166,"LK BRYAN 230.00",1,230,10,"2627 ACSS/TW",null,1195,1195,1195,1195,2012,"Planned","Reliability","Line upgrade"]
["PEF","FL",402883,"INTERCESSION CITY 230.00",402166,"LK BRYAN 230.00",2,230,10,"2627 ACSS/TW",null,1195,1195,1195,1195,2012,"Planned","Reliability","Line upgrade"]
["PEF","FL",403159,"ARCHER 230.00",403171,"HAILE SW 230.00",1,230,null,"2627 ACSS/TW",null,1195,1195,1195,1195,2015,"Planned","Reliability","Line upgrade"]
["PEF","FL",403159,"ARCHER 230.00",403528,"MARTIN W 230.00",1,230,null,"2627 ACSS/TW",null,1195,1195,1195,1195,2015,"Planned","Reliability","Line upgrade"]
["PEF","FL",403163,"FT. WHITE SOUTH 230.00",403174,"GINNIE 230.00",1,230,null,"2627 ACSS/TW",null,1195,1195,1195,1195,2015,"Planned","Reliability","Line upgrade"]
["PEF","FL",403165,"NEWBERRY 230.00",403174,"GINNIE 230.00",1,230,null,"2627 ACSS/TW",null,1195,1195,1195,1195,2015,"Planned","Reliability","Line upgrade"]
["PEF","FL",403171,"HAILE SW 230.00",403174,"GINNIE 230.00",1,230,null,"2627 ACSS/TW",null,1195,1195,1195,1195,2015,"Planned","Reliability","Line upgrade"]

{"sheet":"SCEG","index":20,"n_rows":19,"n_cols":19,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new facilities (161 kV and above) that are projected to be in-service by 2020.  It should be noted whether these are committed or planned."]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["SCE&G","SC",370302,"Graniteville ",370320,"Graniteville",3,"230/115",0,null,null,null,null,null,null,"2010-12-01","Planned","Reliability"]
["SCE&G","SC",370201,"Lake Murray ",370210,"Lake Murray",2,"230/115",0,null,null,null,null,null,null,"2011-05-01","Planned","Reliability"]
["SCE&G","SC",370106,"Denny Terrace",370103,"Pineland",1,230,9,null,null,null,null,null,null,"2011-05-01","Planned","Reliability"]
["SCE&G","SC",370407,"Yemassee",370470,"Yemassee",3,"230/115",0,null,null,null,null,null,null,"2012-05-01","Planned","Reliability"]
["SCE&G","SC",370013,"PepperHill",370507,"Summerville Trans",1,230,8.1999999999999993,null,null,null,null,null,null,"2013-05-01","Planned","Reliability"]
["SCE&G","SC",370701,"Cainhoy",370370,"Cainhoy",1,"230/115",0,null,null,null,null,null,null,"2014-05-01","Planned","Reliability"]
["SCE&G","SC",370204,"CIP",370240,"CIP",2,"230/115",0,null,null,null,null,null,null,"2015-05-01","Planned","Reliability"]
["SCE&G","SC",370201,"Lake Murray ",370210,"Lake Murray",3,"230/115",0,null,null,null,null,null,null,"2015-12-01","Planned","Reliability"]
["SCE&G","SC",370106,"Denny Terrace",370160,"Denny Terrace",3,"230/115",0,null,null,null,null,null,null,"2015-12-01","Planned","Reliability"]
["SCE&G","SC",370021,"VCS Sub 2",370201,"Lake Murray",2,230,19,null,null,null,null,null,null,"2015-12-01","Planned","Reliability"]
["SCE&G","SC",370011,"AM Williams",370701,"Cainhoy",2,230,9,null,null,null,null,null,null,"2016-05-01","Planned","Reliability"]
["SCE&G","SC",370510,"Am Williams",370710,"Cainhoy",2,115,9,null,null,null,null,null,null,"2016-05-01","Planned","Reliability"]
["SCE&G","SC",370302,"Graniteville ",370306,"Urquhart",2,230,17.8,null,null,null,null,null,null,"2016-05-01","Planned","Reliability"]
["SCE&G","SC",370021,"VCS Sub 2",370404,"St. George",2,230,135,null,null,null,null,null,null,"2018-12-01","Planned","Reliability"]

{"sheet":"SCPSA","index":21,"n_rows":30,"n_cols":19,"rows_kept":30,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["SCPSA","SC",311322,"Arcadia",312766,"Garden City",2,115,14.5,null,null,null,null,null,null,2011,"planned","reliability","Arcadia-Garden City 115 kV Line #2"]
["SCPSA","SC",312712,"Hemingway",311384,"Lake City",1,230,19,null,null,null,null,null,null,2012,"planned","reliability","Fold the existing Hemingway-Marion 230 kV Line into the Lake City 230-69 kV Substation"]
["SCPSA","SC",312729,"Marion",311384,"Lake City",1,230,19,null,null,null,null,null,null,2012,"planned","reliability","Fold the existing Hemingway-Marion 230 kV Line into the Lake City 230-69 kV Substation"]
["SCPSA","SC",311688,"Carolina Forest",312813,"Carolina Forest",null,"230/115",null,null,null,null,null,null,null,2012,"planned","reliability","Carolina Forest 230-115 kV Sub"]
["SCPSA","SC",312813,"Carolina Forest",312764,"Dunes",2,115,4,null,null,null,null,null,null,2012,"planned","reliability","Carolina Forest-Dunes115 kV Line #2"]
["SCPSA","SC",311627,"Orangeburg",311628,"Orangeburg",null,"230/115",null,null,null,null,null,null,null,2012,"planned","reliability","Orangeburg 230-115 kV Sub"]
["SCPSA","SC",311612,"Pomaria",312993,"Pomaria",null,"230/69",null,null,null,null,null,null,null,2012,"planned","reliability","Pomaria 230-69 kV Sub"]
["SCPSA","SC",311382,"Winnsboro",311059,"Winnsboro",null,"230/69",null,null,null,null,null,null,null,2013,"planned","reliability","Winnsboro 230-69 kV Sub"]
["SCPSA","SC",370012,"VC Summer",311382,"Winnsboro",1,230,14,null,null,null,null,null,null,2013,"planned","reliability","VC Summer-Winnsboro 230 kV Line"]
["SCPSA","SC",311654,"Richburg",311399,"Richburg",null,"230/69",null,null,null,null,null,null,null,2014,"planned","reliability","Richburg 230-69 kV Sub"]
["SCPSA","SC",311382,"Winnsboro",311654,"Richburg",1,230,26.3,null,null,null,null,null,null,2014,"planned","reliability","Winnsboro-Richburg 230 kV Line"]
["SCPSA","SC",370012,"VC Summer",311612,"Pomaria",2,230,6.93,null,null,null,null,null,null,2014,"planned","reliability","VC Summer-Pomaria 230 kV Line #2"]
["SCPSA","SC",311716,"Bucksville",311717,"Bucksville",null,"230/115",null,null,null,null,null,null,null,2015,"planned","reliability","Bucksville 230-115 kV Sub"]
["SCPSA","SC",311654,"Richburg",312732,"Flat Creek",1,230,32.450000000000003,null,null,null,null,null,null,2015,"planned","reliability","Richburg-Flat Creek 230 kV Line"]
["SCPSA","SC",312719,"Winyah",311716,"Bucksville",1,230,32.5,null,null,null,null,null,null,2016,"planned","reliability","Winyah-Bucksville 230 kV Line"]
["SCPSA","SC",311612,"Pomaria",312737,"Sandy Run",1,230,58,null,null,null,null,null,null,2016,"planned","reliability","Pomaria-Sandy Run 230 kV Line"]
["SCPSA","SC",312737,"Sandy Run",311330,"Sandy Run",null,"230/115",null,null,null,null,null,null,null,2016,"planned","reliability","Sandy Run 230-115 kV Sub"]
["SCPSA","SC",311717,"Bucksville",312766,"Garden City",1,115,15,null,null,null,null,null,null,2017,"planned","reliability","Bucksville-Garden City 115 kV Line"]
["SCPSA","SC",312737,"Sandy Run",311627,"Orangeburg",1,230,33.200000000000003,null,null,null,null,null,null,2017,"planned","reliability","Sandy Run-Orangeburg 230 kV Line"]
["SCPSA","SC",311673,"Wassamassaw",311674,"Wassamassaw",null,"230/115",null,null,null,null,null,null,null,2017,"planned","reliability","Wassamassaw 230-115 kV Sub"]
["SCPSA","SC",312728,"St. George",311393,"St. George",null,"230/115",null,null,null,null,null,null,null,2018,"planned","reliability","St. George 230-115 kV Substation"]
["SCPSA","SC",311627,"Orangeburg",312728,"St. George",1,230,29.07,null,null,null,null,null,null,2018,"planned","reliability","Orangeburg-St. George 230 kV Line"]
["SCPSA","SC",312710,"Cross",311673,"Wassamassaw",2,230,18.3,null,null,null,null,null,null,2018,"planned","reliability","Cross-Wassamassaw 230 kV Line"]
["SCPSA","SC",312728,"St. George",312718,"Varnville",1,230,41.1,null,null,null,null,null,null,2019,"planned","reliability","St. George-Varnville 230 kV Line"]
["SCPSA","SC",312718,"Varnville",312840,"Varnville",null,"230/115",null,null,null,null,null,null,null,2019,"planned","reliability","Construct a new Varnville 230-115 kV Sub"]

{"sheet":"SOCO","index":22,"n_rows":102,"n_cols":19,"rows_kept":102,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["SOCO","AL",385180,"N.OPEL6",385310,"HILLABEE",1,230,37.6,null,null,null,null,null,null,2011,"Planned","Reliability","Upgrade approximately 37.6 mi of 230 kV line to 110 C "]
["SOCO","AL",384215,"HOLT 6",385182,"TUSC6",1,230,6.9,null,null,null,null,null,null,2011,"Planned","Reliability","Construct approximately 6.9 mi of 230 kV line"]
["SOCO","MS",388460,"CARIERSW 230.00",388461,"CARIERSW 115.00",1,"230/115",null,null,null,null,null,null,null,2011,"Planned","Reliability","Construct a new 230/115 kV substation"]
["SOCO","MS",388460,"CARIERSW 230.00",388400,"KILN 230.00",1,230,26.4,null,null,null,null,null,null,2011,"Planned","Reliability","Construct approximately 26.4 mi of 230 kV line"]
["SOCO","GA",389001,"MCINTOSH    230.00",389003,"KRAFT       230.00",1,230,16.3,null,null,null,null,null,null,2012,"Planned","Reliability","Rebuild approximately 16 mi of 230 kV lines "]
["SOCO","GA",389001,"MCINTOSH    230.00",389003,"KRAFT       230.00",2,230,16.3,null,null,null,null,null,null,2012,"Planned","Reliability","Rebuild approximately 16 mi of 230 kV lines "]
["SOCO","AL",384965,"DANWAYSS",385310,"HILLABEE",1,230,32.049999999999997,null,null,null,null,null,null,2012,"Planned","Reliability","Upgrade approximately 32 mi of 230 kV line to 110 C "]
["SOCO","AL",384508,"MONTG SS",384513,"S MONTG6",1,230,7.7,null,null,null,null,null,null,2012,"Planned","Reliability","Reconductor approximately 7.7 mi of 230 kV line"]
["SOCO","GA",389001,"MCINTOSH    230.00",389155,"BLANDFORD 230",1,230,8.6,null,null,null,null,null,null,2013,"Planned","Reliability","Reconductor approximately 18.2 mi of 230 kV line"]
["SOCO","GA",389155,"BLANDFORD 230",389044,"MELDRIM 230",2,230,9.6,null,null,null,null,null,null,2013,"Planned","Reliability","Reconductor approximately 18.2 mi of 230 kV line"]
["SOCO","AL",384471,"GREENCO6 230.00",384470,"GREENCO3 115.00",2,"230/115",null,null,null,null,null,null,null,2013,"Planned","Reliability","Install a new 230/115 kV transformer"]
["SOCO","AL",385178,"AUTAUSS8 500.00",385500,"AUTAUG6 230.00",1,"500/230",null,null,null,null,null,null,null,2013,"Planned","Reliability","Install a new 500/230 kV transformer"]
["SOCO","MS",388000,"MDN NE 230.00",388001,"MDN NE 115.00",1,"230/115",null,null,null,null,null,null,null,2013,"Planned","Reliability","Replace the 230/115 kV transformer"]
["SOCO","MS",388000,"MDN NE 230.00",388001,"MDN NE 115.00",2,"230/115",null,null,null,null,null,null,null,2013,"Planned","Reliability","Replace the 230/115 kV transformer"]
["SOCO","FL",387765,"LAGUNA B 230.00",387836,"L SMITH",1,230,14.2,null,null,null,null,null,null,2013,"Planned","Reliability","Reconductor approximately 14.2 mi of 230 kV line"]
["SOCO","FL",387765,"LAGUNA B 230.00",387766,"LAGUNA B 115.00",2,"230/115",null,null,null,null,null,null,null,2013,"Planned","Reliability","Install a new 230/115 kV transformer"]
["SOCO","GA",389146,"DEAN FOREST",389147,"DEAN FOREST",null,"230/115",null,null,null,null,null,null,null,2014,"Planned","Reliability","Install a 400 MVA, 230/115 kV transformer"]
["SOCO","GA",389175,"BOULEVARD 2",389146,"DEAN FOREST",1,null,null,null,null,null,null,null,null,2014,"Planned","Reliability","Rebuild approximately "]
["SOCO","GA",389001,"MCINTOSH    230.00",389176,"GS-W",1,230,14.3,null,null,null,null,null,null,2014,"Planned","Reliability","Tap the Kraft-McIntosh 230 kV line with new 230 kV station"]
["SOCO","GA",389176,"GS-W",389003,"KRAFT       230.00",1,230,2,null,null,null,null,null,null,2014,"Planned","Reliability","Tap the Kraft-McIntosh 230 kV line with new 230 kV station"]
["SOCO","GA",389146,"DEAN FOREST",389176,"GS-W",1,230,5,null,null,null,null,null,null,2014,"Planned","Reliability","Build approximately 5 mi of new 230 kV line"]
["SOCO","GA",389146,"DEAN FOREST",389003,"KRAFT       230.00",1,230,5.7,null,null,null,null,null,null,2014,"Planned","Reliability","Rebuild approximately 5.7 mi of 230 kV line"]
["SOCO","AL",384400,"GASTON",380179,"ROOPVILLE",1,230,72,null,null,null,null,null,null,2014,"Planned","Reliability","Upgrade approximately 72 mi of 230 kV line"]
["SOCO","AL",385235,"E PELHAM6",384400,"GASTON",1,230,11.97,null,null,null,null,null,null,2014,"Planned","Reliability","Upgrade approximately 11.97 mi of 230 kV line"]
["SOCO","AL",385897,"CO LINE6 230.00",385898,"CO LINE3 115.00",2,"230/115",null,null,null,null,null,null,null,2014,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","AL",384511,"SNOWDN6",385138,"PIKE CO6",1,230,32.299999999999997,null,null,null,null,null,null,2014,"Planned","Reliability","Reconductor approximately 32.3 mi of 230 kV line"]
["SOCO","GA",380317,"ROCKVILLE 500.00",380018,"SCHERER",1,500,54,null,null,null,null,null,null,2015,"Planned","Reliability","Construct new 500 kV Sw St along Scherer-Warthen 500 kV line"]
["SOCO","GA",380317,"ROCKVILLE 500.00",383052,"WARTHEN",1,500,24.5,null,null,null,null,null,null,2015,"Planned","Reliability","Construct new 500 kV Sw St along Scherer-Warthen 500 kV line"]
["SOCO","GA",380017,"E WALTON 500.00",382098,"E WALTON 230.00",1,"500/230",null,null,null,null,null,null,null,2015,"Planned","Reliability","Construct a new 500/230/115 kV Substation"]
["SOCO","GA",380317,"ROCKVILLE 500.00",380017,"E WALTON 500.00",1,500,46.6,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 46.6 mi of new 500 kV line"]
["SOCO","GA",382098,"E WALTON 230.00",382055,"BETHABARA",1,230,13.3,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 13.3 mi of new 230 kV line"]
["SOCO","GA",382098,"E WALTON 230.00",382055,"BETHABARA",2,230,10.130000000000001,null,null,null,null,null,null,2105,"Planned","Reliability","Construct approximately 10.13 mi of new 230 kV line"]
["SOCO","GA",382098,"E WALTON 230.00",382059,"BOSTWICK",1,230,5.45,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 5.45 mi of new 230 kV line"]
["SOCO","GA",382098,"E WALTON 230.00",382799,"JACKS CREEK",1,230,13,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 13 mi of new 230 kV line"]
["SOCO","GA",382059,"BOSTWICK",380122,"E WATKNSV 2",1,230,11.38,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 11.38 mi of new 230 kV line"]
["SOCO","GA",380065,"NORCROSS",380056,"BERKELEY LAKE",1,230,3.5,null,null,null,null,null,null,2015,"Planned","Reliability","Reconductor approximately 3.5 mi of 230 kV line"]
["SOCO","GA",380086,"CUMMING",381977,"SHARON SP 230.00",1,230,6.6,null,null,null,null,null,null,2015,"Planned","Reliability","Construct approximately 6.6 mi of new 230 kV line"]
["SOCO ","GA",381977,"SHARON SP 230.00",382084,"SHARON SP 115.00",1,"230/115",null,null,null,null,null,null,null,2015,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","FL",387776,"S ROSA 230.00",387775,"SNT ROSA 115.00",1,"230/115",null,null,null,null,null,null,null,2015,"Planned","Reliability","Construct a new 230/115 Substation"]
["SOCO","FL",387776,"S ROSA 230.00",387775,"SNT ROSA 115.00",2,"230/115",null,null,null,null,null,null,null,2015,"Planned","Reliability","Construct a new 230/115 Substation"]
["SOCO","FL",387776,"S ROSA 230.00",387765,"LAGUNA B 115.00",1,230,21.35,null,null,null,null,null,null,2015,"Planned","Reliability","Construct a new 230/115 Substation"]
["SOCO","FL",387776,"S ROSA 230.00",387765,"LAGUNA B 115.00",2,230,21.35,null,null,null,null,null,null,2015,"Planned","Reliability","Construct a new 230/115 Substation"]
["SOCO ","GA",380337,"BAY CREEK",381937,"BAY CREEK",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Install a second 230/115 kV transformer"]
["SOCO","GA",380100,"E SOCIAL CIR",382370,"R_ESC B-ESC",1,230,null,null,null,null,null,null,null,2016,"Planned","Reliability","Install a 2% reactor on 230 kV line"]
["SOCO","GA",380147,"BRANCH",380172,"W MILLEDGVL",1,230,6.23,null,null,null,null,null,null,2016,"Planned","Reliability","Bundle approximately 6.23 mi of 230 kV line"]
["SOCO","GA",382224,"CORN CRIB 230.00",382225,"CORN CRIB 115.00",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Construct a new 230/115 kV substation"]
["SOCO","GA",382224,"CORN CRIB",380123,"YATES",1,230,14.8,null,null,null,null,null,null,2016,"Planned","Reliability","Loop in the existing 230 kV line into new substation"]
["SOCO","GA",382224,"CORN CRIB",380169,"THOMASTON",1,230,40.5,null,null,null,null,null,null,2016,"Planned","Reliability","Loop in the existing 230 kV line into new substation"]
["SOCO","GA",380148,"GORDON",380156,"N DUBLIN",1,230,32,null,null,null,null,null,null,2016,"Planned","Reliability","Construct approximately 32 mi of new 230 kV line"]
["SOCO","GA",383070,"APPLING BIO",380224,"OFFERMAN",1,230,27.1,null,null,null,null,null,null,2016,"Planned","Reliability","Reconductor approximately 27.1 mi of 230 kV line"]
["SOCO","GA",381216,"HWY 54",381936,"HWY 54",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Construct a new 230/115 kV substation"]
["SOCO","GA",381216,"HWY 54",380026,"UNION CITY",1,230,9.4,null,null,null,null,null,null,2016,"Planned","Reliability","Loop in the existing 230 kV line into new substation"]
["SOCO","GA",381216,"HWY 54",380174,"NEW HOPE",1,230,7.13,null,null,null,null,null,null,2016,"Planned","Reliability","Loop in the existing 230 kV line into new substation"]
["SOCO","GA",380090,"LAWRENCEVL",380095,"WINDER",1,230,15.3,null,null,null,null,null,null,2016,"Planned","Reliability","Rebuild approximately 15.3 mi of existing 230 kV line"]
["SOCO","GA",380040,"ROSWELL 230.00",380048,"PARKAIRE 230.00",1,230,4.5,null,null,null,null,null,null,2016,"Planned","Reliability","Construct approximately 4.5 mi of new 230 kV line"]
["SOCO","GA",380040,"ROSWELL 230.00",380322,"ROSWELL",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","GA",380149,"S MACON  230.00",380767,"S MACON 115.00",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Replace the existing 230/115 kV transformers"]
["SOCO","GA",380149,"S MACON  230.00",380767,"S MACON 115.00",2,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Replace the existing 230/115 kV transformers"]
["SOCO","GA",380008,"VOGTLE",381490,"THOMSON",1,500,50,null,null,null,null,null,null,2016,"Planned","Reliability","Construct approximately 50 mi of new 500 kV transmission line"]
["SOCO","AL",384638,"CHICK 6",384700,"BARRY 6",1,230,18.43,null,null,null,null,null,null,2016,"Planned","Reliability","Reconductor approximately 18.4 mi of 230 kV line"]
["SOCO","AL",385425,"S.DUNVL6 230.00",385426,"S.DUNVL3",1,"230/115",null,null,null,null,null,null,null,2016,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","GA",380095,"WINDER P 230.00",382021,"CLARKSBORO 230.00",1,230,14,null,null,null,null,null,null,2017,"Planned","Reliability","Reconductor approximately 14.0 mi of 230 kV line"]
["SOCO","GA",382751,"CORNELIA 230.00",380407,"CORNELIA 115.00",1,"230/115",null,null,null,null,null,null,null,2017,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","GA",382751,"CORNELIA 230.00",380091,"MIDDLE FORK 230.00",1,230,10,null,null,null,null,null,null,2017,"Planned","Reliability","Build approximately 10 mi of new 230 kV line"]
["SOCO","GA",380165,"W BRUNSWICK 230.00",382152,"DORCHESTER 230.00",1,230,45,null,null,null,null,null,null,2017,"Planned","Reliability","Build approximately 45 mi of new 230 kV line"]
["SOCO","GA",382152,"DORCHESTER 230.00",382140,"DORCHESTER 115.00",2,"230/115",null,null,null,null,null,null,null,2017,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","GA",382152,"DORCHESTER 230.00",389051,"LT OGEECHEE 230.00",1,230,21.9,null,null,null,null,null,null,2017,"Planned","Reliability","Reconductor approximately 21.9 mi of 230 kV line"]
["SOCO","GA",382470,"E CARROLTON 230.00",382471,"E CARROLTON 115.00",1,"230/115",null,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 230/115 kV substation"]
["SOCO","GA",382470,"E CARROLTON 230.00",382469,"BRIGHT STAR",1,230,5.3,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 230/115 kV substation and loop in 230 kV line"]
["SOCO","GA",382470,"E CARROLTON 230.00",382480,"YELLOW DIRT",1,230,14.1,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 230/115 kV substation and loop in 230 kV line"]
["SOCO","GA",380088,"MCGRAU FORD 230.00",380209,"HOPEWELL    230.00",2,230,11.9,null,null,null,null,null,null,2017,"Planned","Reliability","Construct approximately 11.9 mi of new 230 kV line"]
["SOCO","GA",380006,"MIDDLE FORK 500.00",380091,"MIDDLE FORK 230.00",1,"500/230",null,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 500/230 kV substation "]
["SOCO","GA",380006,"MIDDLE FORK 500.00",306105,"OCONEE 500.00",1,500,null,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 500/230 kV substation and loop in 500 kV line"]
["SOCO","GA",380006,"MIDDLE FORK 500.00",380011,"S HALL 500.00",1,500,25,null,null,null,null,null,null,2017,"Planned","Reliability","Construct a new 500/230 kV substation and loop in 500 kV line"]
["SOCO","GA",380006,"MIDDLE FORK 500.00",381490,"THOMSON 500.00",1,500,90,null,null,null,null,null,null,2017,"Planned","Reliability","Construct approximately 90 mi of new 500 kV line"]
["SOCO","GA",380224,"OFFERMAN 230.00",381093,"OFFERMAN 115.00",3,"230/115",null,null,null,null,null,null,null,2017,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","GA",380016,"OHARA 500.00",380171,"OHARA 230.00",2,"500/230",null,null,null,null,null,null,null,2017,"Planned","Reliability","Install a 500/230 kv transformer"]
["SOCO","GA",381301,"SUWANEE 230.00",382035,"S HALL 230.00",1,230,20,null,null,null,null,null,null,2017,"Planned","Reliability","Construct approximately 20 mi of new 230kV line"]
["SOCO","GA",380171,"OHARA 230.00",381933,"MCDONOUGH 230.00",1,230,20,null,null,null,null,null,null,2017,"Planned","Reliability","Rebuild existing 115 kV to create new 230 kV circuit"]
["SOCO","GA",381933,"MCDONOUGH   230.00",380743,"MCDONOUGH 115.00",1,"230/115",null,null,null,null,null,null,null,2017,"Planned","Reliability","Install a new 230/115 kV transformer"]
["SOCO","GA",380147,"BRANCH 230.00",382325,"R_EATC B-E3 230.00",1,230,11.1,null,null,null,null,null,null,2018,"Planned","Reliability","Install a 2% reactor at 230 kV substation"]
["SOCO","GA",382325,"R_EATC B-E3 230.00",382054,"EATONTON C",1,230,0,null,null,null,null,null,null,2018,"Planned","Reliability","Install a 2% reactor at 230 kV substation"]
["SOCO","GA",380011,"S HALL 500.00",380017,"E WALTON 500.00",1,500,35,null,null,null,null,null,null,2018,"Planned","Reliability","Construct approximately 35 mi of new 500 kV transmission line"]
["SOCO","GA",380089,"GAINSVL#2-1 230.00",380420,"GAINSVL#2-1 115.00",1,"230/115",null,null,null,null,null,null,null,2018,"Planned","Reliability","Replace the existing 230/115 kV transformer"]
["SOCO","GA",389001,"MCINTOSH    230.00",389021,"MCINTOSH 115.00",1,"230/115",null,null,null,null,null,null,null,2018,"Planned","Reliability","Replace the existing 230/115 kV transformer"]
["SOCO","GA",380056,"BERKELEY LK 230.00",381232,"SPRUILL RD",1,230,3.9,null,null,null,null,null,null,2018,"Planned","Reliability","Reconductor approximately 3.9 mi of 230 kV line"]
["SOCO","GA",380066,"SCOTTDALE 230.00",380357,"SCOTTDALE 115.00",2,"230/115",null,null,null,null,null,null,null,2018,"Planned","Reliability","Install a new 230/115 kV transformer"]
["SOCO","GA",381301,"SUWANEE 230.00",381977,"SHARON SP 230.00",1,230,14.5,null,null,null,null,null,null,2018,"Planned","Reliability","Construct approximately 14.5 mi of new 230 kV line"]
["SOCO","GA",380033,"ADAMSVILLE",380034,"BAKERS FRY",1,230,1.6,null,null,null,null,null,null,2019,"Planned","Reliability","Reconductor approximately 1.6 mi of 230 kV line"]
["SOCO","GA",380171,"OHARA 230.00",381912,"JONESBORO 230.00",1,230,8.9,null,null,null,null,null,null,2019,"Planned","Reliability","Reconductor approximately 8.9 mi of 230 kV line"]
["SOCO","GA",380117,"WAYNESBORO 230.00",380562,"WAYNESBORO 115.00",1,"230/115",null,null,null,null,null,null,null,2019,"Planned","Reliability","Replace the existing 230/115 kV transformer"]
["SOCO","GA",382181,"R_WMCINTSH1 230.00",381421,"W MCINTOSH1 230.00",1,230,0,null,null,null,null,null,null,2019,"Planned","Reliability","Install a 1% reactor on the 230 kV line"]
["SOCO","GA",382181,"R_WMCINTSH1 230.00",389001,"MCINTOSH 230.00",1,230,0.43,null,null,null,null,null,null,2019,"Planned","Reliability","Install a 1% reactor on the 230 kV line"]
["SOCO","GA",382182,"R_WMCINTSH2 230.00",381424,"W MCINTOSH2 230.00",1,230,0,null,null,null,null,null,null,2019,"Planned","Reliability","Install a 1% reactor on the 230 kV line"]
["SOCO","GA",382182,"R_WMCINTSH2 230.00",389001,"MCINTOSH 230.00",1,230,0.37,null,null,null,null,null,null,2019,"Planned","Reliability","Install a 1% reactor on the 230 kV line"]
["SOCO","AL",385180,"N.OPEL6 230.00",385181,"N.OPEL3 115.00",2,"230/115",null,null,null,null,null,null,null,2019,"Planned","Reliability","Install a 230/115 kV transformer"]
["SOCO","AL",384700,"BARRY SP",387060,"CRIST SP",1,230,61.5,null,null,null,null,null,null,2019,"Planned","Reliability","Upgrade approximately 61.5 mi of 230 kV line"]

{"sheet":"SPP","index":23,"n_rows":44,"n_cols":13,"rows_kept":44,"cut":false,"hidden":false,"merged":[[284,12,285,12],[286,12,287,12],[0,0,0,12],[1,0,2,12],[3,0,4,0],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,10,4,10],[3,11,4,11],[3,12,4,12],[66,11,71,11],[109,1,111,1],[180,1,185,1],[185,11,190,11],[3,8,4,8],[3,9,4,9],[403,12,404,12],[405,12,406,12],[407,1,413,1],[795,12,796,12],[605,1,608,1],[664,1,666,1],[789,12,790,12],[791,12,792,12],[793,12,794,12],[490,1,494,1],[923,12,924,12],[918,12,919,12],[799,12,800,12],[801,12,802,12],[804,12,805,12],[806,12,807,12],[920,12,921,12],[908,12,909,12],[925,12,926,12],[950,12,951,12],[1069,12,1070,12],[797,12,798,12],[910,12,911,12],[912,12,913,12],[914,12,915,12],[916,12,917,12]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name"]
["SPP","AR",506935,"FLINT CREEK",90002,"OSAGE CREEK",null,345,63," 6/1/2016","Planned","R","Install 22 miles of new 345 kV, 2-954 ACSR line (Flint Creek to Shipe Road). Install 9 miles of 345 kV line from Shipe Road to East Rogers. Install 32 miles of 345 kV line from East Rogers to Osage Creek"]
["SPP","NM/TX",527896,"HOBBS",527916,"MIDLAND",null,345,89,"2012-12-01","Planned","R","Convert existing 89.22 mile Hobbs - Midland 230 kV line to operate at 345 kV."]
["SPP","MO",542982,"IATAN",542980,"NASHUA",1,345,30,"2015-06-01","Planned","R","Tap Nashua 345kV bus in Hawthorn - St. Joseph 345 kV line.  Build new 345 kV line from Iatan to Nashua."]
["SPP","KS/NEB",530583,"KNOLL",640065,"AXTELL",null,345,125,"2013-06-01","Planned","EC","Build new 345 kV line from Knoll to interception point of Axtell to Knoll line. Updated mileage for filed route; reactor added at Post Rock (55 Mvar)"]
["SPP","TX/AR",508072,"NW TEXARKANA",507455,"TURK",1,345,33,"2012-04-01","Planned","TS","Build approximately 33 miles of 2-954 ACSR from Turk to NW Texarkana."]
["SPP","KS",532771,"RENO CO",532773,"SUMMIT",1,345,51,"2010-10-01","Planned","EC","Install new 50.55-mile 345 kV line from Reno county to Summit; Substation work required at Summit for new 345 kV terminal"]
["SPP","KS/OK",532794,"ROSE HILL",514803,"SOONER",1,345,53,"2012-06-01","Planned","R","New 345 kV line from Sooner to Oklahoma/Kansas Stateline or the interface with the Westar Energy line segment to achieve 3000 amp or greater emergency rating."]
["SPP","OK",515045,"SEMINOLE",515224,"MUSKOGEE",1,345,100,"2013-12-31","Planned","R","Build new 345 kV line from Seminole to Muskogee"]
["SPP","KS",531469,"SPEARVILLE",530583,"KNOLL",1,345,90,"2012-06-01","Planned","EC","Build new 345 kV line from Knoll to interception point of Spearville to Knoll line.  Updated for approved route mileage; reflect addition of reactor at Post Rock (35 Mvar)"]
["SPP","TX",521157,"HUGO",510911,"VALLIANT",1,345,19,"2012-04-01","Planned","TS","Install 345 kV terminal equipment at Valliant Substation"]
["SPP","TX/OK",525832,"TUCO",523775,"WOODWARD",1,345,178,"2014-05-19","Planned","R","New 345kV line from Woodward EHV to SPS Tuco"]
["SPP","KS",532861,"EAST MANHATTAN",532862,"MCDOWELL",null,230,null,"2012-06-01","Planned","R","The East Manhattan-McDowell 115 kV is built as a 230 kV line but is operated at 115 kV. Substation work will have to be performed in order to convert this line to 230 kV operation.."]
["SPP","TX",524365,"RANDALL CO.",524415,"AMARILLO S.",1,230,20,"2014-04-01","Planned","R","Build new 20 mile Randall Co - Amarillo South 230 kV line.  Install second 230/115 kV transformer in Randall substation."]
["SPP","TX",526338,"JONES",526677,"GRASSLAND",2,230,18,"2013-06-01","Planned","R","Build new second Jones - Grassland 230 kV line."]
["SPP","NM",524875,"OASIS",524897,"PLEASANT HILL",1,230,16,"2012-06-01","Planned","R","Build new 16 mile Frio - Draw - Oasis 230 kV line. New 230/115 kV transformer at Frio - Draw substation."]
["SPP","NM",524897,"PLEASANT HILL",524909,"ROOSEVELT",1,230,26,"2012-12-01","Planned","R","Build new 26 mile Frio - Draw - Roosevelt County 230 kV line."]
["SPP","TX",525461,"NEWHART",525213,"SWISHER CO.",1,230,19,"2015-04-01","Planned","R","New 19 mile Swisher County Interchange - Newhart 230 kV line to new Newhart substation with 230/115 kV, 150/173 MVA transformer"]
["SPP","TX",523095,"HITCHLAND",523309,"MOORE CO.",1,230,50,"2011-12-01","Planned","R","Build new 50 mile Moore County - Hitchland  230 kV rated at 541 MVA."]
["SPP","TX",523095,"HITCHLAND",523155,"OCHILTREE",1,230,35,"2012-06-01","Planned","R","Add 230 kV line from Hitchland to Ochilltree - 541 MVA."]
["SPP","OGE",515355,"Igo 161 kV",515357,"Razorback 161 kV",1,161,null,"2011-04-01","Planned","PL","Conversion from 69kV to 161kV."]
["SPP","OGE",515358,"Short Mountain 161 kV",515316,"Branch 161 kV",1,161,null,"2011-04-01","Planned","PL","Conversion from 69kV to 161kV."]
["SPP","OGE",503902,"Fitzhugh 161 kV",515327,"Helberg 161 kV",1,161,null,"2011-06-30","Planned","PL","Conversion from 69kV to 161kV."]
["SPP","OGE",515352,"Altus 161 kV",503902,"Fitzhugh 161 kV",1,161,null,"2011-06-30","Planned","PL","Conversion from 69kV to 161kV."]
["SPP","OGE",515319,"Little Spadra 161 kV",515355,"Igo 161 kV   ",1,161,null,"2011-04-01","Planned","PL","Conversion from 69kV to 161kV."]
["SPP","OGE",515353,"Great Lakes Carbon 161 kV",515352,"Altus 161 kV",1,161,null,"2011-06-30","Planned","PL","Conversion from 69kV to 161kV"]
[null,"OGE",515355,"Igo 161 kV",515354,"Noark 161 kV",1,161,null,"2011-06-30","Planned","PL","Conversion from 69kV to 161kV"]
["SPP","OGE",515354,"Noark 161 kV",515353,"Great Lakes Carbon 161 kV",1,161,null,"2011-06-30","Planned","PL","Conversion from 69kV to 161kV"]
["SPP","GRDA",512714,"Kansas Tap 161 kV",512642,"W Siloam Springs 161 kV",1,161,null,"2015-06-01","Planned","R2","Reconductor line to 347MVA"]
["SPP","GRDA",512642,"W Siloam Springs 161 kV",512643,"Siloam City 161 kV",1,161,null,"2015-06-01","Planned","R2","Reconductor line to 347MVA"]
["SPP","KCPL",543069,"Paola 161 kV",543129,"Middle Creek 161 kV",1,161,null,"2013-06-01","Planned","PL","New Middle Creek sub and Paola-Middle Creek 161kV line"]
["SPP","KCPL",543058,"North Louisburg 161 kV",543129,"Middle Creek 161 kV",1,161,null,"2013-06-01","Planned","PL","New North Louisburg-Middle Creek 161kV line"]
["SPP","KCPL",543054,"Cedar Niles 161 kV",{"$error":"#N/A"},"Clare 161 kV",1,161,null,"2012-06-01","Planned","PL","New Cedar Niles-Clare 161 kV Line & Clare substation"]
["SPP","GMO",541346,"Ritchfield 161 kV",541202,"Sibley 161kV",1,161,null,"2010-06-01","Planned","PL","161kV Tap of Hallmark to Sibley"]
["SPP","GMO",541215,"Hallmark 161kV",541346,"Ritchfield 161 kV",1,161,null,"2010-06-01","Planned","PL","161kV Tap of Hallmark to Sibley"]
["SPP","KCPL",543030,"Waldron 161 kV",546656,"Maywood 161 kV",1,161,null,"2013-06-01","Planned","PL","New Waldron sub cut-in"]
["SPP","KCPL",543030,"Waldron 161 kV",543017,"Weatherby 161 kV",1,161,null,"2013-06-01","Planned","PL","New Waldron sub cut-in"]
["SPP","OGE",515300,"Fort Smith 161 kV",515345,"Colony 161 kV",1,161,2.2000000000000002,"2013-06-01","Planned","R","Reconductor 2.2 miles of Fort Smith - Colony 161 kV line to 1590 kcmil ACSR and change terminal equipment at Ft. Smith and Colony substations to 2000A."]
["SPP","KCPL",543130,"Sunflower",542966,"West Gardner",1,161,null,"2013-06-01","Planned","PL","New Sunflower sub and cut-in"]
["SPP","KCPL",543121,"Hillsdale 161 kV",543054,"Cedar Niles 161 kV",1,161,null,"2015-06-01","Planned","R","New Hillsdale - Cedar Niles 161 kV Line and Cedar Niles ring bus."]

{"sheet":"TVA","index":24,"n_rows":169,"n_cols":19,"rows_kept":169,"cut":false,"hidden":false,"merged":[[3,18,4,18],[3,11,3,14],[3,15,4,15],[3,16,4,16],[3,17,4,17],[3,9,3,10],[3,4,3,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[0,0,0,18],[1,0,2,18],[3,0,4,0],[3,1,4,1],[3,2,3,3]]}
["New / Upgraded Transmission Facilities in 2020 Roll-Up Case"]
["Includes ALL new/upgraded facilities (161 kV and above) that are projected to be in-service by 2020.  "]
[]
["PA","State(s)","From Bus",null,"To Bus",null,"Ckt","Voltage","Line Length (mi)","Conductor",null,"Ratings",null,null,null,"Expected In-Service (year)","Under Construction / Planned / Conceptual","Project Type (Reliability or Economic)","Descripton "]
[null,null,"PSSE Bus #","Name","PSSE Bus #","Name",null,null,null,"Size","Type","Summer A","Summer B","Winter A","Winter B"]
["TVA","TN",360011,"Rutherford",360412,"Christiana",1,161,16.079999999999998,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360011,"Rutherford",360386,"East Murfreesboro",1,161,29.1,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360011,"Rutherford",361655,"Rockvale",1,161,7.38,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360012,"Hemlock Semiconductor",360045,"Montgomery 2",1,161,2.6,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360019,"Jackson",360683,"Jackson 2",1,"500/161","N/A",null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360021,"Shelby",360568,"Lagoon Creek",1,500,35.15,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360030,"Lowndes",360539,"Caledonia CT",1,500,0.09,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360035,"West Point",360688,"Clay",1,500,0.08,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360036,"West Point",361615,"Waterway Drive Tap",1,161,26.67,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","MS",360036,"West Point",361496,"Severcorr 2",2,161,20.39,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360038,"Johnsonville Fossil 1-4",361027,"Trace Creek Tap",1,161,3.83,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360041,"Cumberland",360318,"Erin",1,161,5.2,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","KY",360043,"Paradise",361032,"Aberdeen Tap (KY)",1,161,14.9,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360044,"Montgomery ",360045,"Montgomery 2",1,"500/161","N/A",null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",360045,"Montgomery 2",361654,"West Creek",1,161,9.14,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360045,"Montgomery 2",360012,"Hemlock Semiconductor",3,161,2.7,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360048,"Davidson",360581,"Pin Hook",1,500,27.72,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360051,"Maury",361593,"Spring Hill",1,161,6.02,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",360060,"Madison",360088,"Limestone",1,161,23.8,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","AL",360061,"Madison 1",361313,"Redstone Tap 2",1,161,13.23,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",360062,"Bellefonte 1",360065,"Widows Creek",1,500,29.75,null,null,null,null,null,null,"2018-06-18","Planned","Reliability"]
["TVA","AL",360062,"Bellefonte 1",360060,"Madison",1,500,40.82,null,null,null,null,null,null,"2018-06-18","Planned","Reliability"]
["TVA","AL",360063,"Bellefonte 2",360065,"Widows Creek",1,500,21.3,null,null,null,null,null,null,"2018-06-18","Planned","Reliability"]
["TVA","AL",360063,"Bellefonte 2",360058,"East Point",1,500,71,null,null,null,null,null,null,"2018-06-18","Planned","Reliability"]
["TVA","AL-GA",360067,"Widows Creek 2",360414,"Oglethorpe",1,161,30.56,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","AL-GA",360067,"Widows Creek 2",360414,"Oglethorpe",2,161,30.47,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360071,"Wilson",360581,"Pin Hook",1,161,14.18,null,null,null,null,null,null,"2010-11-12","Planned","Reliability"]
["TVA","TN",360081,"Sequoyah",360110,"Hiwassee",1,500,20.5,null,null,null,null,null,null,"2010-11-13","Planned","Reliability"]
["TVA","TN",360084,"Athens (TN)",361403,"Niota",1,161,3.9,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360085,"Watts Bar 1",360093,"Bull Run",1,500,53.91,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360098,"Volunteer 1",360527,"East Knox",1,161,13,null,null,null,null,null,null,"2010-11-13","Planned","Reliability"]
["TVA","TN",360100,"John Sevier 1",360103,"Phipps Bend",1,161,11.85,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360100,"John Sevier 1",360103,"Phipps Bend",3,161,11.91,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360100,"John Sevier 1",360703,"John Sevier CC Units 1-2 Tap",1,161,0,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360100,"John Sevier 1",360705,"John Sevier CC Units 1-2",3,161,0,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360110,"Hiwassee",360085,"Watts Bar 1",1,500,24.5,null,null,null,null,null,null,"2010-11-13","Planned","Reliability"]
["TVA","TN",360111,"Hiwassee",360110,"Hiwassee",1,"500/161","N/A",null,null,null,null,null,null,"2010-11-13","Planned","Reliability"]
["TVA","TN",360112,"Hiwassee",360111,"Hiwassee",2,"500/162","N/A",null,null,null,null,null,null,"2010-11-14","Planned","Reliability"]
["TVA","TN",360133,"Dumplin Valley",360527,"East Knox",1,161,7.8,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360135,"Union City",361406,"South Fifth Union City Tap",1,161,3,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360150,"Alamo (TN)",361658,"Bells ",1,161,6,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",360152,"South Jackson",361640,"Morris Tap",1,161,8.42,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360158,"Covington",361647,"Burlison Tap",1,161,0.15,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360173,"North Lexington",361594,"Lexington",1,161,3.78,null,null,null,null,null,null,"2010-06-14","Planned","Reliability"]
["TVA","MS",360204,"South Philadelphia",361120,"Pearl River Tap",1,161,7.36,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360209,"Corinth",361531,"Biggersville",1,161,8.9,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",360229,"Calhoun City",361607,"Southwest Bruce Tap",1,161,4.8,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360232,"Sturgis",361589,"Northwest Louisville",1,161,12.32,null,null,null,null,null,null,"2010-06-15","Planned","Reliability"]
["TVA","MS",360234,"Lowndes",361624,"Black Warrior Tap",1,161,10.199999999999999,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","MS",360236,"Columbus",361620,"Caldwell Road",1,161,16.36,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",360242,"Philadelphia",360204,"South Philadelphia",1,161,0.9,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","AL",360267,"Wheeler",360268,"Elgin",1,161,5.7,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",360268,"Elgin",360502,"Dunn",1,161,24.46,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360279,"Guntersville",360280,"Guntersville",14,"161/115","N/A",null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",360281,"Limestone",361637,"County Line Road",1,161,6.9,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",360287,"Pisgah",360288,"Henagar",1,161,5.99,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",360288,"Henagar",360286,"Fort Payne",1,161,11.96,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",360291,"Farley",361566,"Big Cove Tap",1,161,4.82,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",360291,"Farley",361650,"Byrd Springs",1,161,4.71,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","AL",360291,"Farley",360279,"Guntersville",1,161,16.68,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360322,"Clarksville",361656,"Gibbs Lane",1,161,5.9,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","KY",360331,"Bowling Green",360540,"Lost City",1,161,26.71,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","KY",360334,"Summer Shade",361603,"East Glasgow Tap",1,161,12.2,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","KY",360336,"Franklin (KY)",361634,"East Simpson Tap",1,161,2.2000000000000002,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360349,"Lebanon",360552,"Lascassas",1,161,19,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360352,"Gallatin  ",360530,"Angeltown",1,161,19.399999999999999,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360352,"Gallatin Fossil 1",360349,"Lebanon",1,161,12.6,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360356,"Springfield",365215,"Goodlettsville (NES)",1,161,15.47,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360356,"Springfield",360358,"North Nashville",1,161,17.309999999999999,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360358,"North Nashville",361192,"Bethel Road",1,161,9.84,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",360385,"Murfreesboro",361651,"Gateway",1,161,1.75,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360399,"Great Falls",361516,"Wheeler Mountain",1,161,25.84,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360433,"Kingston Fossil 7-9",361626,"Kingston Tap",1,161,3.5,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360442,"Elza",361542,"Windrock",1,161,10.86,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360444,"Fort Loudoun",361652,"Poland Creek Tap",1,161,10.24,null,null,null,null,null,null,"2010-11-14","Planned","Reliability"]
["TVA","TN",360448,"Wolf Creek",361618,"Kelsey Road",1,161,14,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360485,"Elizabethton",361494,"Row Branch",1,161,15.87,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",360502,"Dunn",360305,"Mount Pleasant",1,161,26.54,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",360505,"Rally Hill",361657,"Chapel Hill",1,161,11.2,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",360520,"Cross Plains",361613,"White House Tap",1,161,4.2300000000000004,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",360527,"East Knox",360460,"Nixon Road",1,161,11.1,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
[null,"MS",360528,"Clayton Village",361290,"Lakeside",1,161,1,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","MS",360528,"Clayton Village",361610,"Starkville Tap",1,161,4.5999999999999996,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","MS",360528,"Clayton Village",361161,"Catalpa Creek",1,161,9.1,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",360530,"Angeltown",360439,"Portland SS",1,161,9.5500000000000007,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","GA",360533,"Center Point",360621,"Moss Lake",1,230,16.079999999999998,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","GA",360621,"Moss Lake",360622,"Moss Lake",1,"230/115","N/A",null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","GA",360622,"Moss Lake",361442,"Gordon County Tap",1,115,4.4000000000000004,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","GA",360622,"Moss Lake",361486,"Resaca South",1,115,2.67,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",360654,"Choctaw",360035,"West Point",1,500,37.380000000000003,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["MLGW","TN",360678,"Shelby (MLGW) 1",365573,"Bolen Huse (MLGW)",1,161,5.8,null,null,null,null,null,null,"2010-06-15","Planned","Reliability"]
["TVA","MS",360688,"Clay",360654,"Choctaw",1,500,37.380000000000003,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",360689,"Clay",360528,"Clayton Village",1,161,12,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",360690,"Montgomery 1",360012,"Hemlock Semiconductor",1,161,3,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",361027,"Trace Creek Tap",360318,"Erin",1,161,28.87,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361031,"Tennol Tap",361636,"Chicago Bridge & Iron",1,161,0.5,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","KY",361032,"Aberdeen Tap (KY)",360332,"East Bowling Green",1,161,25.64,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","MS",361107,"Egypt Pumping Station Tap",360036,"West Point",1,161,16.18,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361107,"Egypt Pumping Station Tap",360689,"Clay",1,161,16.440000000000001,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361107,"Egypt Pumping Station Tap",360227,"Egypt Pumping Station",1,161,1.75,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361121,"Aberdeen Tap (MS)",360036,"West Point",1,161,10.61,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361121,"Aberdeen Tap (MS)",360689,"Clay",1,161,10.74,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361175,"Langford",361600,"Fannin Tap",1,161,5,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361192,"Bethel Road",365215,"Goodlettsville (NES)",1,161,7.91,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","AL",361224,"Addison",361642,"Helicon",1,161,6.5,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361228,"Moscow Tap (TN)",361628,"Macon Tap (TN)",1,161,4.8499999999999996,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","MS",361255,"Woodson Ridge",361428,"College Hill",1,161,2,null,null,null,null,null,null,"2010-06-11","Conceptual","Reliability"]
["TVA","TN",361267,"Westmoreland",360530,"Angeltown",1,161,6.4,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","GA",361289,"Crawfish Creek",361633,"Cloudland Canyon",1,230,5.59,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361290,"5LAKESIDE MS",360036,"West Point",1,161,13,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361290,"5LAKESIDE MS",360689,"Clay",1,161,13,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","AL",361332,"Sylvania",361645,"Rainsville Industrial Park Tap",1,161,2.46,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361388,"Unionville",361657,"Chapel Hill",1,161,6.09,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","TN",361403,"Niota",361210,"Sweetwater",1,161,7.94,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361406,"South Fifth Union City Tap",361422,"Troy",1,161,6.88,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361411,"Sand Hill",361600,"Fannin Tap",1,161,4.18,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","AL",361438,"Flat Rock Tap",360288,"Henagar",1,161,9.4600000000000009,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","GA",361442,"Gordon County Tap",360626,"Fuller",1,115,3.1,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",361494,"Row Branch",361142,"Elk Mills",1,161,3,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361496,"Severcorr 2",360036,"West Point",1,161,20.28,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361496,"Severcorr 2",360689,"Clay",1,161,20.39,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","GA",361504,"West Ringgold",361514,"West Ringgold",2,"230/115","N/A",null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361516,"Wheeler Mountain",360427,"Spring City",1,161,21.04,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","MS",361529,"Starkville SS",360036,"West Point",1,161,14.19,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361529,"Starkville SS",360689,"Clay",1,161,12.9,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361529,"Starkville SS",361610,"Starkville Tap",1,161,1,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",361542,"Windrock",360445,"Braytown",1,161,3.04,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","MS",361589,"Northwest Louisville",360239,"Louisville",1,161,20.32,null,null,null,null,null,null,"2010-06-15","Planned","Reliability"]
["TVA","TN",361593,"Spring Hill",360531,"Kedron Road",1,161,0.54,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",361594,"Lexington",361319,"West Lexington",1,161,0.75,null,null,null,null,null,null,"2010-06-14","Planned","Reliability"]
["TVA","KY",361603,"East Glasgow Tap",361113,"Glasgow Tap",1,161,5.94,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361607,"Southwest Bruce Tap",360230,"Coffeeville",1,161,18.670000000000002,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361610,"Starkville Tap",360233,"Starkville Tap",1,161,2,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",361613,"White House Tap",361192,"Bethel Road",1,161,4.7,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361615,"Waterway Drive Tap",360225,"Amory",1,161,1.7,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361618,"Kelsey Road",361619,"Byrdstown",1,161,15,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361618,"Kelsey Road",360450,"Huntsville (TN)",1,161,36.659999999999997,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","MS",361620,"Caldwell Road",360234,"Lowndes",1,161,0.12,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","MS",361624,"Black Warrior Tap",361649,"New Hamilton",1,161,1.6,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361626,"Kingston Tap",361214,"Loudon",1,161,14.1,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",361628,"Macon Tap (TN)",361269,"Canadaville",1,161,6.59,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",361631,"Jena",361638,"Niles Ferry",1,161,5.6,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","GA",361633,"Cloudland Canyon",361503,"Kensington",1,230,6.93,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","KY",361634,"East Simpson Tap",361570,"Mitchellville Tap",1,161,5.65,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361636,"Chicago Bridge & Iron",361036,"Tennol",1,161,5.35,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","AL",361637,"County Line Road",360273,"Jetport",1,161,2.4,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",361640,"Morris Tap",361457,"McKellar",1,161,1,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",361645,"Rainsville Industrial Park Tap",361472,"Section",1,161,10.029999999999999,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361647,"Burlison Tap",361338,"Brighton Tap",1,161,5.17,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]
["TVA","MS",361649,"New Hamilton",361125,"Hamilton (MS)",1,161,0.2,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","AL",361650,"Byrd Springs",361313,"Redstone Tap 2",1,161,0.76,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361651,"Gateway",361375,"Blackman Tap",1,161,4,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["TVA","TN",361652,"Poland Creek Tap",360096,"Alcoa SS",1,161,5.28,null,null,null,null,null,null,"2010-11-14","Planned","Reliability"]
["TVA","TN",361654,"West Creek",361443,"Screaming Eagles Tap",1,161,5,null,null,null,null,null,null,"2010-11-10","Under Construction","Reliability"]
["TVA","TN",361655,"Rockvale",360386,"East Murfreesboro",1,161,21.72,null,null,null,null,null,null,"2010-11-11","Planned","Reliability"]
["TVA","TN",361656,"Gibbs Lane",361274,"Saint Bethlehem Tap",1,161,1.96,null,null,null,null,null,null,"2010-06-11","Under Construction","Reliability"]
["MLGW","TN",365573,"Bolen Huse (MLGW) ",365591,"Northeast Gate (MLGW)",1,161,9.77,null,null,null,null,null,null,"2010-06-15","Planned","Reliability"]
["MLGW","TN",365577,"North Primary (MLGW)",365576,"Poplar Avenue (MLGW)",1,161,9.7799999999999994,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["MLGW","TN",365577,"North Primary (MLGW)",365595,"University (MLGW)",1,161,4.1100000000000003,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["MLGW","TN",365591,"Northeast Gate (MLGW)",365593,"Chelsea (MLGW)",1,161,4.1900000000000004,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","TN",365600,"Fite Road",365511,"Fite Road",1,"161/115","N/A",null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["MLGW","TN",365826,"Collierville Gate (MLGW)",365913,"South Collierville (MLGW)",1,161,5.6,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["MLGW","TN",365913,"South Collierville (MLGW)",365827,"Shelton Road (MLGW)",1,161,5.6,null,null,null,null,null,null,"2010-06-13","Planned","Reliability"]
["TVA","KY",366005,"Grahamville",360496,"C-33 (DOE)",1,161,0,null,null,null,null,null,null,"2010-06-12","Planned","Reliability"]